## Shop Schedule
Completed | Document Number | WO Form ID | Start Date | Customer | SO# | Structure # | Item | Description | Quantity
| WO16966 | 120MH | 2026-08-24 | Sunesis Construction Co. | Sales Order #26-1466P3 | 220-8 SS-MH | MH120RSVF | 120" - MH RISER Custom Ht - 34" | 1
| WO18340 | 36MH | 2026-08-24 | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3262 | WQU 1 | MH036BA72 | 36" - MH BASE T/n - 72" | 1
| WO18443 | 48MH | 2026-08-24 |  |  |  | MH048CCN24X |  | 1
| WO18442 | 48MH | 2026-08-24 |  |  |  | MH048CN24X |  | 1
| WO18441 | 48MH | 2026-08-24 |  |  |  | MH048LD12ECC |  | 1
| WO18432 | 48MH | 2026-08-24 |  |  |  | MH048BA36-KO |  | 1
| WO18431 | 48MH | 2026-08-24 |  |  |  | MH048BA36-B |  | 2
| WO18430 | 48MH | 2026-08-24 |  |  |  | MH048RS36 |  | 2
| WO18429 | 48MH | 2026-08-24 |  |  |  | MH048RS48 |  | 4
| WO18428 | 48MH | 2026-08-24 |  |  |  | MH048RS72 |  | 2
| WO18424 | 48MH | 2026-08-24 |  |  |  | MH048LD07-24X36RECT |  | 2
| WO18411 | 48MH | 2026-08-24 | City of Leitchfield | Sales Order #26-3083 | 1 SS-MH | MH048BA18 | 48" - MH BASE T/n - 18" | 1
| WO18396 | 48MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 208 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 26" | 1
| WO18395 | 48MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 207 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 26" | 1
| WO18347 | 48MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 212 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 37" | 1
| WO18346 | 48MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 212 ST-MH | mh048ld07S | 48" - MH FLAT TOP w/30"x30" Hole W/ Recess for Grate - 7" | 1
| WO13393 | 48MH | 2026-08-24 | Connhurst, LLC | Sales Order #26-1066 | A4 (8) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 1
| WO11477 | 48MH | 2026-08-24 |  |  |  | MH048CN36X |  | 1
| WO11188 | 48MH | 2026-08-24 |  |  |  | MH048CN30X |  | 1
| WO11187 | 48MH | 2026-08-24 |  |  |  | MH048CN36X |  | 2
| WO10408 | 48MH | 2026-08-24 | Cumberland Pipeline LLC | Sales Order #26-1322B | 243-88 SS-MH | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1
| WO18369 | 60MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 104 ST-MH | MH060BAVF | 60" - MH BASE Custom Ht - 42" | 1
| WO18264 | 60MH | 2026-08-24 | Sunesis Construction Co. | Sales Order #26-1466P4 | 231-15 SS-MH | MH060BAVF | 60" - MH BASE (08"F) - 71" | 1
| WO18263 | 60MH | 2026-08-24 | Sunesis Construction Co. | Sales Order #26-1466P4 | 231-15 SS-MH | MH060TS13-48ECC | 60" - MH Transition Slab 48" Hole - 13" | 1
| WO17655 | 60MH | 2026-08-24 |  |  |  | MH060LD13 |  | 1
| WO18418 | 72MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 111 ST-MH | MH072LD15-24X36RECT | 72" - MH FLAT TOP w/24"x36" Hole - 15" | 1
| WO18383 | 72MH | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 111 ST-MH | MH072BAVF | 72" - MH BASE Custom Ht - 78" | 1
| WO18200 | 72MH | 2026-08-24 | Pace Contracting, LLC | Sales Order #25-4547P2 | MH-39-01A | MH072RS72 | 72" - MH RISER - 72" | 1
| WO17430 | 84MH | 2026-08-24 | Garney Companies, Inc. | Sales Order #26-1549P2 | MH-5-6 SS-MH | MH084BAEVFX | 84" - MH BASE w/FLANGE (12F/14EF) w/XYPEX - 93" | 1
| WO13567 | 96MH | 2026-08-24 | Pace Contracting, LLC | Sales Order #25-4547 | PROCESS RETURN V.V. | MH096BAEVF | 96" - MH BASE EF Cust. Ht. 12"F (14"EF =142"OD) - 91" | 1
| WO18082 | Symon | 2026-08-24 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL10 | Secondary Pour | SECONDARY POUR - EXT. FLANGE | 1
| WO18448 | BLK | 2026-08-24 |  |  |  | BLK660603 |  | 36
| WO18445 | BLK | 2026-08-24 |  |  |  | BLK242436AB |  | 1
| WO18444 | BLK | 2026-08-24 |  |  |  | BLK242436AT |  | 1
| WO18368 | Boxes | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 103 INM10 | BX2436-06W08F-BAVF | 24" x 36" - BOX BASE 6inW- 8inF- Variable Ht - 44" | 1
| WO18355 | Boxes | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 215 INE7 | BX3030-06W08F-BAVF | 30" x 30" - BOX BASE 6inW- 8inF- Variable Ht - 38" | 1
| WO18289 | Boxes | 2026-08-24 | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,5 DBI13G | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 38" | 1
| WO18286 | Boxes | 2026-08-24 | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,3 DBI3 | BX3636-08BAVF | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 34" | 1
| WO18285 | Boxes | 2026-08-24 | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,2 DBI14 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 26" | 1
| WO18283 | Boxes | 2026-08-24 | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,1 CBIF | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 25" | 1
| WO17975 | Boxes | 2026-08-24 | Hinkle Construction Services, LLC | Sales Order #24-2527B2 | Str 1 CBIA | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 32" | 1
| WO17974 | Boxes | 2026-08-24 | Hinkle Construction Services, LLC | Sales Order #24-2527B2 | Str 2 CBIA | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 32" | 1
| WO17968 | Boxes | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-11 | BX4848-08RVF | 48" x 48" - BOX RISER 8inW- Variable Ht F/G - 15" | 1
| WO17882 | Boxes | 2026-08-24 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 14+27 CBBI-MOD B1 | BX2436-08R-VH | 24" x 36" - BOX RISER 8inW- Variable Ht - 21" | 1
| WO17775 | Boxes | 2026-08-24 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 14+27 CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 42" | 1
| WO17739 | Boxes | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 259 (432+75 LT) | BX2460-08BA36 | 24" x 60" - BOX BASE 8inW- 8inF F/n - 36" | 1
| WO17703 | Boxes | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 276 (438+65 RT) | BX3648-08BAVF | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht F/n - 59" | 1
| WO17613 | Boxes | 2026-08-24 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 460 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 44" | 1
| WO17606 | Boxes | 2026-08-24 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 458 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 1
| WO18446 | FES | 2026-08-24 |  |  |  | FES12B |  | 1
| WO18447 | HW | 2026-08-24 |  |  |  | HWSF15 |  | 1
| WO18311 | HW | 2026-08-24 |  |  |  | HWPC48 |  | 1
| WO18309 | HW | 2026-08-24 |  |  |  | HWSF24 |  | 1
| WO18267 | HW | 2026-08-24 |  |  |  | HWSF18 |  | 1
| WO18111 | JW | 2026-08-24 |  |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  | 4
| WO16982 | JW | 2026-08-24 |  |  |  | MBI-TCCB-10-JJ |  | 36
| WO18439 | KYTC CBI | 2026-08-24 |  |  |  | CBITA5-TS |  | 1
| WO18438 | KYTC CBI | 2026-08-24 |  |  |  | CBITB10-BR |  | 1
| WO18437 | KYTC CBI | 2026-08-24 |  |  |  | CBITB10-T |  | 1
| WO18436 | KYTC CBI | 2026-08-24 |  |  |  | CBITA10-BR |  | 1
| WO18435 | KYTC CBI | 2026-08-24 |  |  |  | CBITA10-TR |  | 1
| WO18434 | KYTC CBI | 2026-08-24 |  |  |  | CBITA10-BL |  | 1
| WO18433 | KYTC CBI | 2026-08-24 |  |  |  | CBITA10-TL |  | 1
| WO17794 | KYTC MBI | 2026-08-24 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5082+33 RT CBBI-MOD B1 (Top Phase) | CMBBIT9-B1RH | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 1
| WO18450 | RCP | 2026-08-24 |  |  |  | PIPRCP663 |  | 1
| WO18449 | RCP | 2026-08-24 |  |  |  | PIPRCP214 |  | 16
| WO18416 | RCP | 2026-08-24 |  |  |  | PIPRCP3860ELLP3 |  | 8
| WO18318 | RCP | 2026-08-24 | McCreary Concrete Products, Inc. | Sales Order #26-3435 |  | PIPRCP243SP | 24in RCP Class 3 Special, No Lift Holes | 904
| WO18229 | RET | 2026-08-24 |  |  |  | RET-FORIX-60-BC |  | 4
| WO18256 | RET | 2026-08-24 |  |  |  | RET-SS-3SF-CG |  | 2
| WO16179 | RET | 2026-08-24 |  |  |  | RET-SS-MID-CAP |  | 1
| WO16178 | RET | 2026-08-24 |  |  |  | RET-SS-6-28-CG |  | 2
| WO16177 | RET | 2026-08-24 |  |  |  | RET-SS-24-44T-CG |  | 1
| WO16176 | RET | 2026-08-24 |  |  |  | RET-SS-24-86-CG |  | 4
| WO16175 | RET | 2026-08-24 |  |  |  | RET-SS-24-44-CG |  | 3
| WO16174 | RET | 2026-08-24 |  |  |  | RET-FORIX-PARCP |  | 1
| WO16173 | RET | 2026-08-24 |  |  |  | RET-FORIX-PAR-BC |  | 2
| WO16172 | RET | 2026-08-24 |  |  |  | RET-FORIX-PAR-BC |  | 2
| WO16170 | RET | 2026-08-24 |  |  |  | RET-FORIX-84-BC |  | 4
| WO16169 | RET | 2026-08-24 |  |  |  | RET-FORIX-30-BC |  | 22
| WO18147 | Secondary Activity | 2026-08-24 | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-23 | PSASSEMBLY | ASSEMBLY REQUIRED | 1
| WO17718 | Symon | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 247 (428+75 LT) | BX024060-08LD08-1559 | 24" x 60" - BX FLAT LID 8inW- w/15"x59" HOLE (KYTC DBI-13S) F/F - 8" | 1
| WO18360 | Symon | 2026-08-24 | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 218 ST-MH | MH108TS18-48ECC | 108" - MH Transition Slab 48" Hole - 18" | 1
| WO18284 | Symon | 2026-08-24 | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,2 DBI14 | BX024024-08LD08-14 | 24" x 24" - CB FLAT TOP 8"W (HOE KY-210) F/F - 8" | 1
| WO18165 | Symon | 2026-08-24 | Core & Main LP (BG) #113 | Sales Order #26-2495 | QL1 | BX072132-08LD06S | 72" x 132" - CB FLAT TOP 6"W w/48" X 48" HATCH F/F - 8" | 1
| WO18084 | Symon | 2026-08-24 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL11 VV | BX072072-08BA-VH | 72" x 72" - BOX BASE 8inW- 8inF- Variable Ht - 64" | 1
| WO18077 | Symon | 2026-08-24 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL7 VV | BX072072-08BA-VH | 72" x 72" - BOX BASE 8inW- 8inF- Variable Ht - 64" | 1
| WO18070 | Symon | 2026-08-24 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL4 VV | Secondary Pour | SECONDARY POUR - WALLS | 1
| WO18068 | Symon | 2026-08-24 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL4 VV | BX072072-08TS-S | 72" x 72" - CB FLAT TOP 8"W w/37"X36 Hatch - 8" | 1
| WO17910 | Symon | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 257 (431+95 LT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 1
| WO17772 | Symon | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 229 (423+15 RT) | BX036036-08TS024036 | 36" x 36" - CB TRANSITION SLAB 24"X36" HOLE T/F - 8" | 1
| WO17736 | Symon | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 235 (425+04 RT) | BX024030-08LD08-15x27 | 24" x 30" - CB FLAT TOP 8"W w/15"x27" HOLE F/F - 8" | 1
| WO17698 | Symon | 2026-08-24 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 267 (435+52 RT) | BX4848_08TS8 | 48" x 48" - CB FT REDUCER 48" HOLE T/F - 8" | 1
| WO17225 | Symon | 2026-08-24 | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 1 - BC 5.67x3.00 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 68" x 36" | 1
| WO16753 | Symon | 2026-08-24 | Mechanical Consultants Inc | Sales Order #26-2018 | M.V. MV-2 | BX072120-08LD08S | 72" x 120" - CB FLAT TOP 8"W w/30"x30" HATCH - 8" | 1
| WO16751 | Symon | 2026-08-24 | Mechanical Consultants Inc | Sales Order #26-2018 | M.V. MV-1 | BX072120-08LD08S | 72" x 120" - CB FLAT TOP 8"W w/30"x30" HATCH - 8" | 1
| WO16584 | Symon | 2026-08-24 | Endesol, Inc. | Sales Order #26-2945 | QL1 | CTS | 96" - Combined Lift Station Top Slab Custom - 12" | 1
| WO16524 | Symon | 2026-08-24 | Hinkle Construction Services, LLC | Sales Order #26-1463 | 2 | BX054168-08LD08-S | 54" x 168" - BX FLAT TOP 8"W w/(2) 30"x36" HATCHES - 8" | 1
| WO14846 | Symon | 2026-08-24 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P17-P18 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1
| WO14845 | Symon | 2026-08-24 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P17-P18 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1
| WO14844 | Symon | 2026-08-24 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P16-P17 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1
| WO13005 | Symon | 2026-08-24 | Endesol, Inc. | Sales Order #26-1617 | 2-61617 1 | CVR | 50" x 252" - BOX RISER 6inW- Variable Ht F/G - 28" | 1
| WO06248 | Symon | 2026-08-24 | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 240" MIT Section B - 32" x 240" MIT Section B - 32" x 234" | 1
| WO06034 | Symon | 2026-08-24 | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 78" MIT Section D - 32" x 78" MIT Section D - 32" x 78" | 1
| WO06033 | Symon | 2026-08-24 | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 78" MIT Section D - 32" x 78" MIT Section D - 32" x 78" | 1

## WorkOrderProductionScheduleRes
Internal ID | Document Number | Status | WO Form ID | Start Date | End Date | Form ID | Customer | SO# | Structure # | Item | Description | Concrete Weight | Quantity | Stack-It PART - DrawingImage | QR Label | Submittal Drawing link | Scheduling Method | Expected Ship Date
4 | WO16966 | Released | 120MH | 2026-08-24 | 2026-08-26 | 120MH | Sunesis Construction Co. | Sales Order #26-1466P3 | 220-8 SS-MH | MH120RSVF | 120" - MH RISER Custom Ht - 34" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P3%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520%2520-%2520202607002P/26-1466%2520220-8%2520SS-MH%2520P4%2520MH120RSVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P3%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520%2520-%2520202607002P/26-1466%2520220-8%2520SS-MH%2520P4%2520MH120RSVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P3%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520%2520-%2520202607002P/26-1466%2520220-8%2520SS-MH%2520Submittal.pdf
101.0 | WO18340 | Released | 36MH | 2026-08-24 | 2026-08-26 | 36MH | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3262 | WQU 1 | MH036BA72 | 36" - MH BASE T/n - 72" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3262%2520ADS%2520Anchorage%2520Middletown%2520Fire%2520Station%252036%2520-%25202026080158/26-3262%2520WQU%25201%2520P1%2520MH036BA72%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3262%2520ADS%2520Anchorage%2520Middletown%2520Fire%2520Station%252036%2520-%25202026080158/26-3262%2520WQU%25201%2520P1%2520MH036BA72%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3262%2520ADS%2520Anchorage%2520Middletown%2520Fire%2520Station%252036%2520-%25202026080158/26-3262%2520WQU%25201%2520Submittal.pdf
| WO18443 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048CCN24X |  |  | 1
| WO18442 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048CN24X |  |  | 1
| WO18441 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048LD12ECC |  |  | 1
| WO18432 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048BA36-KO |  |  | 1
| WO18431 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048BA36-B |  |  | 2
| WO18430 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048RS36 |  |  | 2
| WO18429 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048RS48 |  |  | 4
| WO18428 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048RS72 |  |  | 2
| WO18424 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH |  |  |  | MH048LD07-24X36RECT |  |  | 2
1.0 | WO18411 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH | City of Leitchfield | Sales Order #26-3083 | 1 SS-MH | MH048BA18 | 48" - MH BASE T/n - 18" | 0.66432 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3083%2520PO%2520No-36293%25204-%2520DIA%2520Sanitary%2520Manhole%2520-%25202026070168/26-3083%25201%2520SS-MH%2520P1%2520MH048BA18%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3083%2520PO%2520No-36293%25204-%2520DIA%2520Sanitary%2520Manhole%2520-%25202026070168/26-3083%25201%2520SS-MH%2520P1%2520MH048BA18%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3083%2520PO%2520No-36293%25204-%2520DIA%2520Sanitary%2520Manhole%2520-%25202026070168/26-3083%25201%2520SS-MH%2520Submittal.pdf
22.0 | WO18396 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 208 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 26" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520208%2520ST-MH%2520P1%2520MH048BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520208%2520ST-MH%2520P1%2520MH048BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520208%2520ST-MH%2520Submittal.pdf
23.0 | WO18395 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 207 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 26" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520207%2520ST-MH%2520P1%2520MH048BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520207%2520ST-MH%2520P1%2520MH048BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520207%2520ST-MH%2520Submittal.pdf
12.0 | WO18347 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 212 ST-MH | MH048BAVF | 48" - MH BASE Custom Ht - 37" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520P1%2520MH048BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520P1%2520MH048BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520Submittal.pdf
12.0 | WO18346 | Released | 48MH | 2026-08-24 | 2026-08-27 | 48MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 212 ST-MH | mh048ld07S | 48" - MH FLAT TOP w/30"x30" Hole W/ Recess for Grate - 7" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520P2%2520MH048LD07S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520P2%2520MH048LD07S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520212%2520ST-MH%2520Submittal.pdf
7.0 | WO13393 | Released | 48MH | 2026-08-24 | 2026-08-25 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A4 (8) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 0.8 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A4%2520%25288%2529%2520P3%2520MH048CN42-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A4%2520%25288%2529%2520P3%2520MH048CN42-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A4%2520%25288%2529%2520Submittal.pdf
| WO11477 | Released | 48MH | 2026-08-24 | 2026-08-26 | 48MH |  |  |  | MH048CN36X |  |  | 1
| WO11188 | Released | 48MH | 2026-08-24 | 2026-08-26 | 48MH |  |  |  | MH048CN30X |  |  | 1
| WO11187 | Released | 48MH | 2026-08-24 | 2026-08-26 | 48MH |  |  |  | MH048CN36X |  |  | 2
118.0 | WO10408 | Released | 48MH | 2026-08-24 | 2026-08-26 | 48MH | Cumberland Pipeline LLC | Sales Order #26-1322B | 243-88 SS-MH | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1.003 | 1
18.0 | WO18369 | Released | 60MH | 2026-08-24 | 2026-08-27 | 60MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 104 ST-MH | MH060BAVF | 60" - MH BASE Custom Ht - 42" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520104%2520ST-MH%2520P1%2520MH060BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520104%2520ST-MH%2520P1%2520MH060BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520104%2520ST-MH%2520Submittal.pdf
1.0 | WO18264 | Released | 60MH | 2026-08-24 | 2026-08-26 | 60MH | Sunesis Construction Co. | Sales Order #26-1466P4 | 231-15 SS-MH | MH060BAVF | 60" - MH BASE (08"F) - 71" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520P1%2520MH060BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520P1%2520MH060BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520Submittal.pdf
1.0 | WO18263 | Released | 60MH | 2026-08-24 | 2026-08-26 | 60MH | Sunesis Construction Co. | Sales Order #26-1466P4 | 231-15 SS-MH | MH060TS13-48ECC | 60" - MH Transition Slab 48" Hole - 13" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520P2%2520MH060TS13-48ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520P2%2520MH060TS13-48ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1466P4%2520-%2520Lower%2520Mill%2520Creek%2520HWDW%2520Protection%2520-%2520202608004P/26-1466%2520231-15%2520SS-MH%2520Submittal.pdf
| WO17655 | Released | 60MH | 2026-08-24 | 2026-08-26 | 60MH |  |  |  | MH060LD13 |  |  | 1
6.0 | WO18418 | Released | 72MH | 2026-08-24 | 2026-08-27 | 72MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 111 ST-MH | MH072LD15-24X36RECT | 72" - MH FLAT TOP w/24"x36" Hole - 15" | 2.2 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520P2%2520MH072LD15-24X36RECT%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520P2%2520MH072LD15-24X36RECT%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520Submittal.pdf
6.0 | WO18383 | Released | 72MH | 2026-08-24 | 2026-08-27 | 72MH | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 111 ST-MH | MH072BAVF | 72" - MH BASE Custom Ht - 78" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520P1%2520MH072BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520P1%2520MH072BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520111%2520ST-MH%2520Submittal.pdf
101.0 | WO18200 | Released | 72MH | 2026-08-24 | 2026-08-26 | 72MH | Pace Contracting, LLC | Sales Order #25-4547P2 | MH-39-01A | MH072RS72 | 72" - MH RISER - 72" | 2.6955 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520P2%2520MH072RS72%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520P2%2520MH072RS72%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520Submittal.pdf
104.0 | WO17430 | Released | 84MH | 2026-08-24 | 2026-08-28 | 84MH | Garney Companies, Inc. | Sales Order #26-1549P2 | MH-5-6 SS-MH | MH084BAEVFX | 84" - MH BASE w/FLANGE (12F/14EF) w/XYPEX - 93" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-5-6%2520SS-MH%2520P1%2520MH084BAEVFX%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-5-6%2520SS-MH%2520P1%2520MH084BAEVFX%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-5-6%2520SS-MH%2520Submittal.pdf
3.0 | WO13567 | Released | 96MH | 2026-08-24 | 2026-08-26 | 96MH | Pace Contracting, LLC | Sales Order #25-4547 | PROCESS RETURN V.V. | MH096BAEVF | 96" - MH BASE EF Cust. Ht. 12"F (14"EF =142"OD) - 91" | 4.1005 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520V.V.%2520P1%2520MH096BAEVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520V.V.%2520P1%2520MH096BAEVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520V.V.%2520Submittal.pdf
| WO18448 | Released | BLK | 2026-08-24 | 2026-08-27 | BLK |  |  |  | BLK660603 |  |  | 36
| WO18445 | Released | BLK | 2026-08-24 | 2026-08-27 | BLK |  |  |  | BLK242436AB |  |  | 1
| WO18444 | Released | BLK | 2026-08-24 | 2026-08-27 | BLK |  |  |  | BLK242436AT |  |  | 1
19.0 | WO18368 | Released | Boxes | 2026-08-24 | 2026-08-28 | Boxes | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 103 INM10 | BX2436-06W08F-BAVF | 24" x 36" - BOX BASE 6inW- 8inF- Variable Ht - 44" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520103%2520INM10%2520P1%2520BX2436-06W08F-BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520103%2520INM10%2520P1%2520BX2436-06W08F-BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520103%2520INM10%2520Submittal.pdf
14.0 | WO18355 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 215 INE7 | BX3030-06W08F-BAVF | 30" x 30" - BOX BASE 6inW- 8inF- Variable Ht - 38" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520215%2520INE7%2520P1%2520BX3030-06W08F-BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520215%2520INE7%2520P1%2520BX3030-06W08F-BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520215%2520INE7%2520Submittal.pdf
13.0 | WO18289 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,5 DBI13G | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 38" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.5%2520DBI13G%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.5%2520DBI13G%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.5%2520DBI13G%2520Submittal.pdf
11.0 | WO18286 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,3 DBI3 | BX3636-08BAVF | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 34" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.3%2520DBI3%2520P1%2520BX3636-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.3%2520DBI3%2520P1%2520BX3636-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.3%2520DBI3%2520Submittal.pdf
10.0 | WO18285 | Released | Boxes | 2026-08-24 | 2026-08-26 | Boxes | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,2 DBI14 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 26" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520P1%2520BX2424-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520P1%2520BX2424-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520Submittal.pdf
9.0 | WO18283 | Released | Boxes | 2026-08-24 | 2026-08-25 | Boxes | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,1 CBIF | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 25" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.1%2520CBIF%2520P1%2520BX2424-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.1%2520CBIF%2520P1%2520BX2424-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.1%2520CBIF%2520Submittal.pdf
2.0 | WO17975 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Hinkle Construction Services, LLC | Sales Order #24-2527B2 | Str 1 CBIA | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 32" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25201%2520CBIA%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25201%2520CBIA%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25201%2520CBIA%2520Submittal.pdf
1.0 | WO17974 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Hinkle Construction Services, LLC | Sales Order #24-2527B2 | Str 2 CBIA | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 32" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25202%2520CBIA%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25202%2520CBIA%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-2527B%2520-%2520KYTC%2520Nelson%2520Co%2520Call%2520105%2520%2528241107%2529%2520-%2520202607002W/24-2527B%2520Str%25202%2520CBIA%2520Submittal.pdf
113.0 | WO17968 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-11 | BX4848-08RVF | 48" x 48" - BOX RISER 8inW- Variable Ht F/G - 15" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-11%2520P2%2520BX4848-08RVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-11%2520P2%2520BX4848-08RVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-11%2520Submittal.pdf
14.0 | WO17882 | Released | Boxes | 2026-08-24 | 2026-08-26 | Boxes | Cleary Construction, Inc. | Sales Order #25-1684P14 | 14+27 CBBI-MOD B1 | BX2436-08R-VH | 24" x 36" - BOX RISER 8inW- Variable Ht - 21" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520P2%2520BX2436-08R-VH%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520P2%2520BX2436-08R-VH%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520Submittal.pdf
14.0 | WO17775 | Released | Boxes | 2026-08-24 | 2026-08-26 | Boxes | Cleary Construction, Inc. | Sales Order #25-1684P14 | 14+27 CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 42" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%252014%252B27%2520CBBI-MOD%2520B1%2520Submittal.pdf
127.0 | WO17739 | Released | Boxes | 2026-08-24 | 2026-08-28 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 259 (432+75 LT) | BX2460-08BA36 | 24" x 60" - BOX BASE 8inW- 8inF F/n - 36" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520259%2520%2528432%252B75%2520LT%2529%2520P1%2520BX2460-08BA36%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520259%2520%2528432%252B75%2520LT%2529%2520P1%2520BX2460-08BA36%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520259%2520%2528432%252B75%2520LT%2529%2520Submittal.pdf
137.0 | WO17703 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 276 (438+65 RT) | BX3648-08BAVF | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht F/n - 59" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520276%2520%2528438%252B65%2520RT%2529%2520P1%2520BX3648-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520276%2520%2528438%252B65%2520RT%2529%2520P1%2520BX3648-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520276%2520%2528438%252B65%2520RT%2529%2520Submittal.pdf
130.0 | WO17613 | Released | Boxes | 2026-08-24 | 2026-08-27 | Boxes | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 460 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 44" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520460%2520P1%2520BX24300808VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520460%2520P1%2520BX24300808VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520460%2520Submittal.pdf
127.0 | WO17606 | Released | Boxes | 2026-08-24 | 2026-08-26 | Boxes | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 458 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520458%2520P1%2520BX24300808VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520458%2520P1%2520BX24300808VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520458%2520Submittal.pdf
| WO18446 | Released | FES | 2026-08-24 | 2026-08-27 | FES |  |  |  | FES12B |  |  | 1
| WO18447 | Released | HW | 2026-08-24 | 2026-08-27 | HW |  |  |  | HWSF15 |  |  | 1
| WO18311 | Released | HW | 2026-08-24 | 2026-08-26 | HW |  |  |  | HWPC48 |  |  | 1
| WO18309 | Released | HW | 2026-08-24 | 2026-08-26 | HW |  |  |  | HWSF24 |  |  | 1
| WO18267 | Released | HW | 2026-08-24 | 2026-08-26 | HW |  |  |  | HWSF18 |  |  | 1
| WO18111 | Released | JW | 2026-08-24 | 2026-08-26 | JW |  |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  |  | 4
| WO16982 | Released | JW | 2026-08-24 | 2026-08-26 | JW |  |  |  | MBI-TCCB-10-JJ |  |  | 36
| WO18439 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITA5-TS |  |  | 1
| WO18438 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITB10-BR |  |  | 1
| WO18437 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITB10-T |  |  | 1
| WO18436 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITA10-BR |  |  | 1
| WO18435 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITA10-TR |  |  | 1
| WO18434 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITA10-BL |  |  | 1
| WO18433 | Released | KYTC CBI | 2026-08-24 | 2026-08-27 | KYTC CBI |  |  |  | CBITA10-TL |  |  | 1
8.0 | WO17794 | Released | KYTC MBI | 2026-08-24 | 2026-08-26 | KYTC MBI | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5082+33 RT CBBI-MOD B1 (Top Phase) | CMBBIT9-B1RH | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205082%252B33%2520RT%2520CBBI-MOD%2520B1%2520P2%2520CMBBIT9-B1RH%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205082%252B33%2520RT%2520CBBI-MOD%2520B1%2520P2%2520CMBBIT9-B1RH%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205082%252B33%2520RT%2520CBBI-MOD%2520B1%2520Submittal.pdf
| WO18450 | Released | RCP | 2026-08-24 | 2026-08-27 | RCP |  |  |  | PIPRCP663 |  |  | 1
| WO18449 | Released | RCP | 2026-08-24 | 2026-08-27 | RCP |  |  |  | PIPRCP214 |  |  | 16
| WO18416 | Released | RCP | 2026-08-24 | 2026-08-26 | RCP |  |  |  | PIPRCP3860ELLP3 |  |  | 8
101.0 | WO18318 | Released | RCP | 2026-08-24 | 2026-08-27 | RCP | McCreary Concrete Products, Inc. | Sales Order #26-3435 |  | PIPRCP243SP | 24in RCP Class 3 Special, No Lift Holes | 66.6893 | 904
| WO18229 | Planned | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-FORIX-60-BC |  |  | 4
| WO18256 | Released | RET | 2026-08-24 | 2026-08-26 | RET |  |  |  | RET-SS-3SF-CG |  |  | 2
| WO16179 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-SS-MID-CAP |  |  | 1
| WO16178 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-SS-6-28-CG |  |  | 2
| WO16177 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-SS-24-44T-CG |  |  | 1
| WO16176 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-SS-24-86-CG |  |  | 4
| WO16175 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-SS-24-44-CG |  |  | 3
| WO16174 | Released | RET | 2026-08-24 | 2026-08-25 | RET |  |  |  | RET-FORIX-PARCP |  |  | 1
| WO16173 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-FORIX-PAR-BC |  |  | 2
| WO16172 | Released | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-FORIX-PAR-BC |  |  | 2
| WO16170 | Planned | RET | 2026-08-24 | 2026-08-24 | RET |  |  |  | RET-FORIX-84-BC |  |  | 4
| WO16169 | Released | RET | 2026-08-24 | 2026-08-25 | RET |  |  |  | RET-FORIX-30-BC |  |  | 22
101.0 | WO18147 | Released | Secondary Activity | 2026-08-24 | 2026-08-25 | Secondary Activity | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-23 | PSASSEMBLY | ASSEMBLY REQUIRED | 1.003 | 1 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQDKVdOYv7pGSoLqiJWIaWmqAc_emSwv_IiWCvHum6qlZ_Q?e=lWDHos
117.0 | WO17718 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 247 (428+75 LT) | BX024060-08LD08-1559 | 24" x 60" - BX FLAT LID 8inW- w/15"x59" HOLE (KYTC DBI-13S) F/F - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520247%2520%2528428%252B75%2520LT%2529%2520P2%2520BX024060-08LD08-1559%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520247%2520%2528428%252B75%2520LT%2529%2520P2%2520BX024060-08LD08-1559%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520247%2520%2528428%252B75%2520LT%2529%2520Submittal.pdf
1.0 | WO18360 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Dan Cristiani Excavating Co. Inc. | Sales Order #26-2212 | 218 ST-MH | MH108TS18-48ECC | 108" - MH Transition Slab 48" Hole - 18" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520218%2520ST-MH%2520P2%2520MH108TS18-48ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520218%2520ST-MH%2520P2%2520MH108TS18-48ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2212%2520-%2520CDTI%2520Building%25201%2520-%25202026070053/26-2212%2520218%2520ST-MH%2520Submittal.pdf
10.0 | WO18284 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Steve Pleasant Excavating, LLC | Sales Order #26-2648 | 4,2 DBI14 | BX024024-08LD08-14 | 24" x 24" - CB FLAT TOP 8"W (HOE KY-210) F/F - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520P2%2520BX024024-08LD08-14%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520P2%2520BX024024-08LD08-14%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2648%2520Midtown%2520Commons%2520Apartments%2520-%25202026060228/26-2648%25204.2%2520DBI14%2520Submittal.pdf
1.0 | WO18165 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Core & Main LP (BG) #113 | Sales Order #26-2495 | QL1 | BX072132-08LD06S | 72" x 132" - CB FLAT TOP 6"W w/48" X 48" HATCH F/F - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2495%2520Campbell%2520View%2520Apartments%2520Vault%2520-%25202026050318/26-2495%2520QL1%2520P2%2520BX072132-08LD06S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2495%2520Campbell%2520View%2520Apartments%2520Vault%2520-%25202026050318/26-2495%2520QL1%2520P2%2520BX072132-08LD06S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2495%2520Campbell%2520View%2520Apartments%2520Vault%2520-%25202026050318/26-2495%2520QL1%2520Submittal.pdf
5.0 | WO18084 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL11 VV | BX072072-08BA-VH | 72" x 72" - BOX BASE 8inW- 8inF- Variable Ht - 64" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL11%2520VV%2520P1%2520BX072072-08BA-VH%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL11%2520VV%2520P1%2520BX072072-08BA-VH%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL11%2520VV%2520Submittal.pdf
2.0 | WO18082 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL10 | Secondary Pour | SECONDARY POUR - EXT. FLANGE | 1.003 | 1
7.0 | WO18077 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL7 VV | BX072072-08BA-VH | 72" x 72" - BOX BASE 8inW- 8inF- Variable Ht - 64" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL7%2520VV%2520P1%2520BX072072-08BA-VH%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL7%2520VV%2520P1%2520BX072072-08BA-VH%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL7%2520VV%2520Submittal.pdf
6.0 | WO18070 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL4 VV | Secondary Pour | SECONDARY POUR - WALLS | 1.003 | 1
6.0 | WO18068 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL4 VV | BX072072-08TS-S | 72" x 72" - CB FLAT TOP 8"W w/37"X36 Hatch - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL4%2520VV%2520P2%2520BX072072-08TS-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL4%2520VV%2520P2%2520BX072072-08TS-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL4%2520VV%2520Submittal.pdf
125.0 | WO17910 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 257 (431+95 LT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 0.5 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520257%2520%2528431%252B95%2520LT%2529%2520P2%2520BX036048-08TS024036%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520257%2520%2528431%252B95%2520LT%2529%2520P2%2520BX036048-08TS024036%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520257%2520%2528431%252B95%2520LT%2529%2520Submittal.pdf
102.0 | WO17772 | Released | Symon | 2026-08-24 | 2026-08-28 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 229 (423+15 RT) | BX036036-08TS024036 | 36" x 36" - CB TRANSITION SLAB 24"X36" HOLE T/F - 8" | 0.5 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520229%2520%2528423%252B15%2520RT%2529%2520P2%2520BX036036-08TS024036%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520229%2520%2528423%252B15%2520RT%2529%2520P2%2520BX036036-08TS024036%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520229%2520%2528423%252B15%2520RT%2529%2520Submittal.pdf
105.0 | WO17736 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 235 (425+04 RT) | BX024030-08LD08-15x27 | 24" x 30" - CB FLAT TOP 8"W w/15"x27" HOLE F/F - 8" | 0.4 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520235%2520%2528425%252B04%2520RT%2529%2520P2%2520BX024030-08LD08-15X27%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520235%2520%2528425%252B04%2520RT%2529%2520P2%2520BX024030-08LD08-15X27%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520235%2520%2528425%252B04%2520RT%2529%2520Submittal.pdf
133.0 | WO17698 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 267 (435+52 RT) | BX4848_08TS8 | 48" x 48" - CB FT REDUCER 48" HOLE T/F - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520267%2520%2528435%252B52%2520RT%2529%2520P2%2520BX4848_08TS8%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520267%2520%2528435%252B52%2520RT%2529%2520P2%2520BX4848_08TS8%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520267%2520%2528435%252B52%2520RT%2529%2520Submittal.pdf
103.0 | WO17225 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 1 - BC 5.67x3.00 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 68" x 36" | 0.1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2504%2520UK%2520BP9%2520Site%2520Thermal%2520and%2520Electric%2520Utilities%2520-%25202025120161/25-2504%2520BC%2520RUN%25201%2520-%2520BC%25205.67x3.00%2520P8%2520CBC%2520Shop.pdf
8.0 | WO16753 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Mechanical Consultants Inc | Sales Order #26-2018 | M.V. MV-2 | BX072120-08LD08S | 72" x 120" - CB FLAT TOP 8"W w/30"x30" HATCH - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-2%2520P2%2520BX072120-08LD08S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-2%2520P2%2520BX072120-08LD08S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-2%2520Submittal.pdf
7.0 | WO16751 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Mechanical Consultants Inc | Sales Order #26-2018 | M.V. MV-1 | BX072120-08LD08S | 72" x 120" - CB FLAT TOP 8"W w/30"x30" HATCH - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-1%2520P2%2520BX072120-08LD08S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-1%2520P2%2520BX072120-08LD08S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2018%2520-%2520Hancock%2520County%2520Middle%2520School%2520Addition%2520-%2520202606005T/26-2018%2520M.V.%2520MV-1%2520Submittal.pdf
1.0 | WO16584 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Endesol, Inc. | Sales Order #26-2945 | QL1 | CTS | 96" - Combined Lift Station Top Slab Custom - 12" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2945%2520-%2520The%2520Cumberlands%2520Lift%2520Station%2520-%25202026070063/26-2945%2520Combo%2520Lift%2520Station%2520P3%2520CTS%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2945%2520-%2520The%2520Cumberlands%2520Lift%2520Station%2520-%25202026070063/26-2945%2520Combo%2520Lift%2520Station%2520P3%2520CTS%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2945%2520-%2520The%2520Cumberlands%2520Lift%2520Station%2520-%25202026070063/26-2945%2520Combo%2520Lift%2520Station%2520Submittal.pdf
| WO16524 | Released | Symon | 2026-08-24 | 2026-08-28 | Symon | Hinkle Construction Services, LLC | Sales Order #26-1463 | 2 | BX054168-08LD08-S | 54" x 168" - BX FLAT TOP 8"W w/(2) 30"x36" HATCHES - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1463%2520-%2520Brown%2520Co%2520Landfill%2520Vaults%2520-%2520202604006S/26-1463%25202%2520P2%2520BX054168-08LD08-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1463%2520-%2520Brown%2520Co%2520Landfill%2520Vaults%2520-%2520202604006S/26-1463%25202%2520P2%2520BX054168-08LD08-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1463%2520-%2520Brown%2520Co%2520Landfill%2520Vaults%2520-%2520202604006S/26-1463%25202%2520Submittal.pdf
17.0 | WO14846 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P17-P18 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520P2%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520P2%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520Submittal.pdf
17.0 | WO14845 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P17-P18 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520P3%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520P3%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P17-P18%2520Submittal.pdf
16.0 | WO14844 | Released | Symon | 2026-08-24 | 2026-08-26 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P16-P17 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P16-P17%2520P1%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P16-P17%2520P1%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P16-P17%2520Submittal.pdf
1.0 | WO13005 | Released | Symon | 2026-08-24 | 2026-08-27 | Symon | Endesol, Inc. | Sales Order #26-1617 | 2-61617 1 | CVR | 50" x 252" - BOX RISER 6inW- Variable Ht F/G - 28" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1617%2520-%25207-27%2520691254032%2520-%25202026030141/26-1617%25202-61617%25201%2520P2%2520CVR%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1617%2520-%25207-27%2520691254032%2520-%25202026030141/26-1617%25202-61617%25201%2520P2%2520CVR%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1617%2520-%25207-27%2520691254032%2520-%25202026030141/26-1617%25202-61617%25201%2520Submittal.pdf
2.0 | WO06248 | Released | Symon | 2026-08-24 | 2026-08-28 | Symon | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 240" MIT Section B - 32" x 240" MIT Section B - 32" x 234" | 1.003 | 1 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQDy3q7J5TgKQ5UdTQRrPxA8AUzJ02t-1d522XIqxmBEXIs?e=SO80Bz | https://icastinc.sharepoint.com/:b:/s/StackIT/IQDaixRjt301TYEHCJOLne0kAWjxcw6A8gFVA5ykPB-9M6k?e=gbjg4K
4.0 | WO06034 | Released | Symon | 2026-08-24 | 2026-08-28 | Symon | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 78" MIT Section D - 32" x 78" MIT Section D - 32" x 78" | 1.003 | 1 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQAaFAH1Cp_dSbea92RwNc-LAfY3HtJem2L69Rl6wrgyZrQ?e=q2VKV3 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQDOL1obEjdfQrZ3mpc6cmcDAUaPvq5OvkdxIa-Jo23TQQU?e=95KPLt
2.0 | WO06033 | Released | Symon | 2026-08-24 | 2026-08-28 | Symon | Birmingham Industrial Construction | Sales Order #25-1110 | MIT-L - MIT Modular Wall/Footing Left | CVBS | 32" x 78" MIT Section D - 32" x 78" MIT Section D - 32" x 78" | 1.003 | 1 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQAaFAH1Cp_dSbea92RwNc-LAfY3HtJem2L69Rl6wrgyZrQ?e=q2VKV3 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQDOL1obEjdfQrZ3mpc6cmcDAUaPvq5OvkdxIa-Jo23TQQU?e=95KPLt