## Shop Schedule
Completed | Document Number | WO Form ID | Start Date | Customer | SO# | Structure # | Item | Description | Quantity
| WO12314 | 48MH | 2026-05-23 | Stock |  |  | MH048CN42 |  | 1
| WO12313 | 48MH | 2026-05-23 | Stock |  |  | MH048CN30 |  | 2
| WO12312 | 48MH | 2026-05-23 | Stock |  |  | MH048CN36 |  | 1
| WO12306 | 48MH | 2026-05-23 | Stock |  |  | MH048RS60X |  | 1
| WO12293 | 48MH | 2026-05-23 | Stock |  |  | MH048LD07-30SQ |  | 2
| WO12292 | 48MH | 2026-05-23 | Stock |  |  | MH048LD12ECC |  | 2
| WO11890 | 48MH | 2026-05-23 | Citco Water | Sales Order #25-4279 | 117+51 ARV | MH048LD12ECC | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 1
| WO11624 | 48MH | 2026-05-23 | Hayes Pipe Supply | Sales Order #26-1219 | 4-8 SS-MH | MH048CCN36CDARED | 48" - CON CONE w/24" HOLE- w/ConBlock-CDA Red - 36" | 1
| WO10918 | 48MH | 2026-05-23 | Winwater Hartford KY Co. | Sales Order #25-1431P3 | 269 (170) | MH048CN30-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 30" | 1
| WO10913 | 48MH | 2026-05-23 | Winwater Hartford KY Co. | Sales Order #25-1431P3 | 276 (169) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 1
| WO11268 | 60MH | 2026-05-23 | Louisville Paving and Construction | Sales Order #25-3452 | S213 | MH060RS36S | 60" - MH RISER SPECIAL - 36" | 1
| WO09203 | 60MH | 2026-05-23 | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | MH060INVFG | 60" - MH INVERT CHANNEL - FULL HEIGHT | 1
| WO09134 | 60MH | 2026-05-23 | Lykins Contracting LLC | Sales Order #25-3118 | 2301539 | MH060BAVF | 60" - MH BASE (10"F) Custom Ht T/n - 72" | 1
| WO09107 | 60MH | 2026-05-23 | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | MH060TS15-48ECC | 60" - MH Transition Slab 48" Hole T/G - 15" | 1
| WO11779 | 72MH | 2026-05-23 | Contech Engineering Solutions | Sales Order #26-2225 | 10-CS-6 | MH072LD15-30ECC | 72" - MH FLAT TOP SPEC. (30" ECC HOLE) F/G - 15" | 1
| WO12038 | 72MH | 2026-05-23 | Russell's Excavating | Sales Order #26-1227 | 106-16 MHK | MH072BAVF | 72" - MH BASE Custom Ht - 67" | 1
| WO11780 | 72MH | 2026-05-23 | Contech Engineering Solutions | Sales Order #26-2225 | 10-CS-6 | MH072RS24S | 72" - MH RISER NO STEPS T/G - 24" | 1
| WO12305 | Boxes | 2026-05-23 | Stock |  |  | BX2424-08B36-KO |  | 1
| WO12304 | Boxes | 2026-05-23 | Stock |  |  | BX2424-06B30-KO |  | 1
| WO11809 | Boxes | 2026-05-23 | Louisville Paving and Construction | Sales Order #25-2952 | 77 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 40" | 1
| WO11793 | Boxes | 2026-05-23 | Louisville Paving and Construction | Sales Order #25-2952 | 125 | BX1818-06RVF | 18" x 18" - BOX RISER 6inW- Variable Ht F/G - 12" | 1
| WO11251 | Boxes | 2026-05-23 | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-D2 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 1
| WO11248 | Boxes | 2026-05-23 | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | OCS-B1 | BX363608R-VF | 36" x 36" - BOX RISER 8inW- Variable Ht - 44" | 1
| WO11243 | Boxes | 2026-05-23 | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-A3 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 49" | 1
| WO11241 | Boxes | 2026-05-23 | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-A1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 56" | 1
| WO12309 | FES | 2026-05-23 | Stock |  |  | FES18B |  | 1
| WO12308 | FES | 2026-05-23 | Stock |  |  | FES15B |  | 1
| WO12307 | FES | 2026-05-23 | Stock |  |  | FES12B |  | 1
| WO12311 | RCP | 2026-05-23 | Stock |  |  | PIPRCP663 |  | 8
| WO12310 | RCP | 2026-05-23 | Stock |  |  | piprcp213 |  | 8
| WO12303 | RET | 2026-05-23 | Stock |  |  | RET-FORIX-CNR-BC |  | 1
| WO12302 | RET | 2026-05-23 | Stock |  |  | RET-FORIX-PAR-BC |  | 1
| WO12301 | RET | 2026-05-23 | Stock |  |  | RET-FORIX-48-BC |  | 5
| WO12300 | RET | 2026-05-23 | Stock |  |  | RET-FORIX-36-BC |  | 5
| WO12299 | RET | 2026-05-23 | Stock |  |  | RET-FORIX-30-BC |  | 5
| WO12298 | RET | 2026-05-23 | Stock |  |  | RET-SS-24-44-CG |  | 2
| WO12297 | RET | 2026-05-23 | Stock |  |  | RET-SS-6-28-CG |  | 2
| WO12296 | RET | 2026-05-23 | Stock |  |  | RET-SS-24-86D150R |  | 2
| WO12295 | RET | 2026-05-23 | Stock |  |  | RET-SS-24-86D150F-CG |  | 2
| WO12294 | RET | 2026-05-23 | Stock |  |  | RET-SS-MID-CAP |  | 2
| WO11710 | BC | 2026-05-23 | Bowen Engineering Corporation | Sales Order #25-2073P3 | BC 4 x 2 (PC 6) | BC048024-08WLF | 48" x 24" - BOX CULVERT (08W/08F/08T) No Haunch G/T - 69" | 1
| WO06496 | Symon | 2026-05-23 | Dan Cristiani Excavating Co. Inc. | Sales Order #25-4299P4 | D3 | BX18180606VF | 18" x 18" - BOX BASE 6inW- 6inF- Variable Ht F/n - 14" | 1
| WO11524 | Symon | 2026-05-23 | Frederick & May Construction Co. | Sales Order #24-4171 | METER VAULT - 10 | Secondary Pour | SECONDARY POUR - Walls | 1
| WO11522 | Symon | 2026-05-23 | Frederick & May Construction Co. | Sales Order #24-4171 | METER VAULT - 9 | Secondary Pour | SECONDARY POUR - Walls | 1
| WO09124 | Symon | 2026-05-23 | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | Secondary Pour | SECONDARY POUR - Add Exterior Drop to Base (P1) | 1

## WorkOrderProductionScheduleRes
Internal ID | Document Number | Status | WO Form ID | Start Date | End Date | Form ID | Customer | SO# | Structure # | Item | Description | Concrete Weight | Quantity | Stack-It PART - DrawingImage | QR Label | Submittal Drawing link | Scheduling Method | Expected Ship Date
| WO12314 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048CN42 |  |  | 1
| WO12313 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048CN30 |  |  | 2
| WO12312 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048CN36 |  |  | 1
| WO12306 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048RS60X |  |  | 1
| WO12293 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048LD07-30SQ |  |  | 2
| WO12292 | Released | 48MH | 2026-05-23 | 2026-05-28 | 48MH | Stock |  |  | MH048LD12ECC |  |  | 2
109.0 | WO11890 | Released | 48MH | 2026-05-23 | 2026-05-26 | 48MH | Citco Water | Sales Order #25-4279 | 117+51 ARV | MH048LD12ECC | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 0.8 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%2520117%252B51%2520ARV%2520P3%2520MH048LD12ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%2520117%252B51%2520ARV%2520P3%2520MH048LD12ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%2520117%252B51%2520ARV%2520Submittal.pdf
105.0 | WO11624 | Released | 48MH | 2026-05-23 | 2026-05-26 | 48MH | Hayes Pipe Supply | Sales Order #26-1219 | 4-8 SS-MH | MH048CCN36CDARED | 48" - CON CONE w/24" HOLE- w/ConBlock-CDA Red - 36" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1219%2520-%25201662%2520Pinkerton%2520Road%2520-%2520202508003T/26-1219%25204-8%2520SS-MH%2520P2%2520MH048CCN36CDARED%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1219%2520-%25201662%2520Pinkerton%2520Road%2520-%2520202508003T/26-1219%25204-8%2520SS-MH%2520P2%2520MH048CCN36CDARED%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1219%2520-%25201662%2520Pinkerton%2520Road%2520-%2520202508003T/26-1219%25204-8%2520SS-MH%2520Submittal.pdf
24.0 | WO10918 | Released | 48MH | 2026-05-23 | 2026-05-26 | 48MH | Winwater Hartford KY Co. | Sales Order #25-1431P3 | 269 (170) | MH048CN30-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 30" | 0.51457 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-269%2520P3%2520MH048CN30-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-269%2520P3%2520MH048CN30-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-269%2520Submittal.pdf
22.0 | WO10913 | Released | 48MH | 2026-05-23 | 2026-05-26 | 48MH | Winwater Hartford KY Co. | Sales Order #25-1431P3 | 276 (169) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 0.8 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-276%2520P3%2520MH048CN42-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-276%2520P3%2520MH048CN42-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1431%2520-%2520Georgetown%2520Commons%2520-%25202026030013/25-1431%2520SSMH-276%2520Submittal.pdf
8.0 | WO11268 | Released | 60MH | 2026-05-23 | 2026-05-27 | 60MH | Louisville Paving and Construction | Sales Order #25-3452 | S213 | MH060RS36S | 60" - MH RISER SPECIAL - 36" | 0.96482 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3452%2520-%2520Churchill%2520Downs%2520Skye%2520Terrace%2520Improvements%2520-%2520202603004Q/25-3452%2520S213%2520P2%2520MH060RS36S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3452%2520-%2520Churchill%2520Downs%2520Skye%2520Terrace%2520Improvements%2520-%2520202603004Q/25-3452%2520S213%2520P2%2520MH060RS36S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3452%2520-%2520Churchill%2520Downs%2520Skye%2520Terrace%2520Improvements%2520-%2520202603004Q/25-3452%2520S213%2520Submittal.pdf
139.0 | WO09203 | Released | 60MH | 2026-05-23 | 2026-05-27 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | MH060INVFG | 60" - MH INVERT CHANNEL - FULL HEIGHT | 1.003 | 1
140.0 | WO09134 | Released | 60MH | 2026-05-23 | 2026-05-28 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301539 | MH060BAVF | 60" - MH BASE (10"F) Custom Ht T/n - 72" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301539%2520P1%2520MH060BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301539%2520P1%2520MH060BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301539%2520Submittal.pdf
139.0 | WO09107 | Released | 60MH | 2026-05-23 | 2026-05-26 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | MH060TS15-48ECC | 60" - MH Transition Slab 48" Hole T/G - 15" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301538%2520P4%2520MH060TS15-48ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301538%2520P4%2520MH060TS15-48ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301538%2520Submittal.pdf
6.0 | WO12038 | Released | 72MH | 2026-05-23 | 2026-05-28 | 72MH | Russell's Excavating | Sales Order #26-1227 | 106-16 MHK | MH072BAVF | 72" - MH BASE Custom Ht - 67" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520106-16%2520MHK%2520P1%2520MH072BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520106-16%2520MHK%2520P1%2520MH072BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520106-16%2520MHK%2520Submittal.pdf
101.0 | WO11780 | Released | 72MH | 2026-05-23 | 2026-05-26 | 72MH | Contech Engineering Solutions | Sales Order #26-2225 | 10-CS-6 | MH072RS24S | 72" - MH RISER NO STEPS T/G - 24" | 0.89849 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520P3%2520MH072RS24S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520P3%2520MH072RS24S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520Submittal.pdf
101.0 | WO11779 | Released | 72MH | 2026-05-23 | 2026-05-26 | 72MH | Contech Engineering Solutions | Sales Order #26-2225 | 10-CS-6 | MH072LD15-30ECC | 72" - MH FLAT TOP SPEC. (30" ECC HOLE) F/G - 15" | 2 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520P4%2520MH072LD15-30ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520P4%2520MH072LD15-30ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2225%2520852136%2520Trace%2520Diecast%2520-%25202026050038/26-2225%252010-CS-6%2520Submittal.pdf
6.0 | WO11710 | Released | BC | 2026-05-23 | 2026-05-27 | BC | Bowen Engineering Corporation | Sales Order #25-2073P3 | BC 4 x 2 (PC 6) | BC048024-08WLF | 48" x 24" - BOX CULVERT (08W/08F/08T) No Haunch G/T - 69" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2073%2520-%2520Alcoa%2520Outfall%2520-%25202026010021/25-2073%2520BC%25204%2520x%25202%2520%2528PC%25206%2529%2520P1%2520BC048024-08WLF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2073%2520-%2520Alcoa%2520Outfall%2520-%25202026010021/25-2073%2520BC%25204%2520x%25202%2520%2528PC%25206%2529%2520P1%2520BC048024-08WLF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2073%2520-%2520Alcoa%2520Outfall%2520-%25202026010021/25-2073%2520BC%25204%2520x%25202%2520%2528PC%25206%2529%2520Submittal.pdf
| WO12305 | Released | Boxes | 2026-05-23 | 2026-05-28 | Boxes | Stock |  |  | BX2424-08B36-KO |  |  | 1
| WO12304 | Released | Boxes | 2026-05-23 | 2026-05-28 | Boxes | Stock |  |  | BX2424-06B30-KO |  |  | 1
1.0 | WO11809 | Released | Boxes | 2026-05-23 | 2026-05-28 | Boxes | Louisville Paving and Construction | Sales Order #25-2952 | 77 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 40" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%252077%2520P1%2520BX2424-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%252077%2520P1%2520BX2424-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%252077%2520Submittal.pdf
1.0 | WO11793 | Released | Boxes | 2026-05-23 | 2026-05-26 | Boxes | Louisville Paving and Construction | Sales Order #25-2952 | 125 | BX1818-06RVF | 18" x 18" - BOX RISER 6inW- Variable Ht F/G - 12" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520125%2520P2%2520BX1818-06RVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520125%2520P2%2520BX1818-06RVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520125%2520Submittal.pdf
| WO11251 | Released | Boxes | 2026-05-23 | 2026-05-27 | Boxes | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-D2 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-D2%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-D2%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-D2%2520Submittal.pdf
| WO11248 | Released | Boxes | 2026-05-23 | 2026-05-27 | Boxes | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | OCS-B1 | BX363608R-VF | 36" x 36" - BOX RISER 8inW- Variable Ht - 44" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520OCS-B1%2520P2%2520BX363608R-VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520OCS-B1%2520P2%2520BX363608R-VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520OCS-B1%2520Submittal.pdf
| WO11243 | Released | Boxes | 2026-05-23 | 2026-05-27 | Boxes | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-A3 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 49" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A3%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A3%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A3%2520Submittal.pdf
| WO11241 | Released | Boxes | 2026-05-23 | 2026-05-27 | Boxes | Core & Main LP (BG) #113 : Core & Main LP (Lou) | Sales Order #25-4733 | CI-A1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 56" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A1%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A1%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4733%2520-%2520%2520The%2520Paddock%2520-%2520202604007S/25-4733%2520CI-A1%2520Submittal.pdf
4.0 | WO06496 | Released | Boxes | 2026-05-23 | 2026-05-26 | Boxes | Dan Cristiani Excavating Co. Inc. | Sales Order #25-4299P4 | D3 | BX18180606VF | 18" x 18" - BOX BASE 6inW- 6inF- Variable Ht F/n - 14" | 0.11658 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4299%2520-%2520Seneca%2520High%2520School%2520-%25202025120181/25-4299%2520D3%2520P1%2520BX18180606VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4299%2520-%2520Seneca%2520High%2520School%2520-%25202025120181/25-4299%2520D3%2520P1%2520BX18180606VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4299%2520-%2520Seneca%2520High%2520School%2520-%25202025120181/25-4299%2520D3%2520Submittal.pdf
| WO12309 | Released | FES | 2026-05-23 | 2026-05-28 | FES | Stock |  |  | FES18B |  |  | 1
| WO12308 | Released | FES | 2026-05-23 | 2026-05-27 | FES | Stock |  |  | FES15B |  |  | 1
| WO12307 | Released | FES | 2026-05-23 | 2026-05-28 | FES | Stock |  |  | FES12B |  |  | 1
| WO12311 | Released | RCP | 2026-05-23 | 2026-05-28 | RCP | Stock |  |  | PIPRCP663 |  |  | 8
| WO12310 | Released | RCP | 2026-05-23 | 2026-05-28 | RCP | Stock |  |  | piprcp213 |  |  | 8
| WO12303 | Released | RET | 2026-05-23 | 2026-05-27 | RET | Stock |  |  | RET-FORIX-CNR-BC |  |  | 1
| WO12302 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-FORIX-PAR-BC |  |  | 1
| WO12301 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-FORIX-48-BC |  |  | 5
| WO12300 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-FORIX-36-BC |  |  | 5
| WO12299 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-FORIX-30-BC |  |  | 5
| WO12298 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-SS-24-44-CG |  |  | 2
| WO12297 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-SS-6-28-CG |  |  | 2
| WO12296 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-SS-24-86D150R |  |  | 2
| WO12295 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-SS-24-86D150F-CG |  |  | 2
| WO12294 | Released | RET | 2026-05-23 | 2026-05-28 | RET | Stock |  |  | RET-SS-MID-CAP |  |  | 2
110.0 | WO11524 | Released | Symon | 2026-05-23 | 2026-05-26 | Symon | Frederick & May Construction Co. | Sales Order #24-4171 | METER VAULT - 10 | Secondary Pour | SECONDARY POUR - Walls | 1.003 | 1
109.0 | WO11522 | Released | Symon | 2026-05-23 | 2026-05-26 | Symon | Frederick & May Construction Co. | Sales Order #24-4171 | METER VAULT - 9 | Secondary Pour | SECONDARY POUR - Walls | 1.003 | 1
139.0 | WO09124 | Released | Symon | 2026-05-23 | 2026-05-27 | Symon | Lykins Contracting LLC | Sales Order #25-3118 | 2301538 | Secondary Pour | SECONDARY POUR - Add Exterior Drop to Base (P1) | 1.003 | 1