## Shop Schedule
Completed | Document Number | WO Form ID | Start Date | Customer | SO# | Structure # | Item | Description | Quantity
| WO15519 | 36MH | 2026-07-16 | ADS Advanced Drainage Systems, Inc. | Sales Order #26-2604 | AR3PC | MH036RS18 | 36" - MH RISER T/G - 18" | 1
| WO15771 | 48MH | 2026-07-16 | Stock |  |  | MH048RS36 |  | 2
| WO15768 | 48MH | 2026-07-16 | Stock |  |  | MH048CN36 |  | 2
| WO15767 | 48MH | 2026-07-16 | Stock |  |  | MH048LD07C |  | 3
| WO15756 | 48MH | 2026-07-16 | Stock |  |  | MH048LD12-24X36RECT |  | 2
| WO13785 | 48MH | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310 | PMH1 SS-MH | MH048CCN36CDARED | 48" - CON CONE w/24" HOLE- w/ConBlock-CDA Red - 36" | 1
| WO15071 | 48MH | 2026-07-16 | Citco Water | Sales Order #25-4212P3 | A11 REV.A | MH048CN24-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 24" | 1
| WO13397 | 48MH | 2026-07-16 | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 1
| WO15733 | 48MH | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310P2 | MH 082-09-371 SS-MH | MH048LD12SCDARED | 48" - MH FLAT TOP w/32" Hole CC w/ConBlock-CDA Red - 12" | 1
| WO15423 | 48MH | 2026-07-16 | Contech Engineered Solutions | Sales Order #26-2877 | 20-CS-4 | MH048LD12-30 | 48" - MH FLAT LID w/30in ECC Hole F/G - 12" | 1
| WO15749 | 48MH | 2026-07-16 | Contech Engineered Solutions | Sales Order #26-2920 | 10-CS-4 | MH048RS24 | 48" - MH RISER T/G - 24" | 1
| WO15746 | 48MH | 2026-07-16 | Contech Engineered Solutions | Sales Order #26-2920 | 10-CS-4 | MH048BA18 | 48" - MH BASE T/n - 18" | 1
| WO15734 | 48MH | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310P2 | MH 082-09-371 SS-MH | MH048BA24CDARED | 48" - MH BASE w/ConBlock-CDA Red - 24" | 1
| WO15663 | 48MH | 2026-07-16 | Cumberland Pipeline LLC | Sales Order #25-4288P2 | A3 | MH048RS72X | 48" - MH RISER w/XYPEX - 72" | 1
| WO15395 | 48MH | 2026-07-16 | Contech Engineered Solutions | Sales Order #26-2877 | 20-CS-4 | MH048RS72S | 48" - MH RISER SPECIAL T/G - 72" | 1
| WO13398 | 48MH | 2026-07-16 | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048RS60S | 48" - MH RISER NO STEPS - 60" | 1
| WO14326 | 48MH | 2026-07-16 | Bear Construction, LLC | Sales Order #25-1401 | R29A | MH048INV14G | 48" - STORM INVERT CHANNEL - 1/4 HEIGHT | 1
| WO13790 | 48MH | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310 | PMH2 SS-MH | MH048INVFCDARED | 48" - MH INVERT CHANNEL w/ConBlock-CDA Red - FULL HEIGHT | 1
| WO13787 | 48MH | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310 | PMH1 SS-MH | MH048INVFCDARED | 48" - MH INVERT CHANNEL w/ConBlock-CDA Red - FULL HEIGHT | 1
| WO13400 | 48MH | 2026-07-16 | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1
| WO14320 | FES | 2026-07-16 | Bear Construction, LLC | Sales Order #25-1401 | R23 | DRAINSLOPE | 28" x 28" - STORM INVERT CHANNEL (FLAT) - 4" THK | 1
| WO13396 | 48MH | 2026-07-16 | Connhurst, LLC | Sales Order #26-1066 | A4 (8) | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1
| WO14360 | 60MH | 2026-07-16 | Bear Construction, LLC | Sales Order #25-1401 | R44 | MH060INV14G | 60" - STORM INVERT CHANNEL - 1/4 HEIGHT | 1
| WO15576 | 60MH | 2026-07-16 | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | SCUM WW | MH060BAEVF | 60" - MH BASE w/FLANGE (08F/07EF) - 43" | 1
| WO09210 | 60MH | 2026-07-16 | Lykins Contracting LLC | Sales Order #25-3118 | 2301560 | MH060DPVF | 60" - MH BASE (10"F) w/DROP Custom Ht T/n - 62" | 1
| WO09119 | 60MH | 2026-07-16 | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | MH060RSVF-D | 60" - MH RISER w/DROP Custom Ht T/G - 52" | 1
| WO14358 | 60MH | 2026-07-16 | Bear Construction, LLC | Sales Order #25-1401 | R44 | MH060LD08SP | 60" - MH FLAT TOP - TDOT D-RJB-1 (SOLID) F/F - 8" | 1
| WO09118 | 60MH | 2026-07-16 | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | MH060TS15-48ECC | 60" - MH Transition Slab 48" Hole T/G - 15" | 1
| WO13280 | 72MH | 2026-07-16 | Endesol, Inc. | Sales Order #26-1355 | Lift Station | CTRS-X | 72" - Combined Lift Station Walls/Floor w/XYPEX - 71" | 1
| WO13556 | 84MH | 2026-07-16 | Pace Contracting, LLC | Sales Order #25-4547 | PROCESS RETURN P.S. | MH084LD17SP | 84" - MH FLAT TOP w/48"x60" Hatch - 17" | 1
| WO14020 | 144MH | 2026-07-16 | Contech Engineered Solutions | Sales Order #26-2692 | 10-CS-12 | MH144RSVF | 144" - MH RISER Custom Ht T/G - 64" | 1
| WO15744 | Boxes | 2026-07-16 | Double A Services, Inc. | Sales Order #26-2989 | QL1 DBI13G | BX2430-08B36-KO | Knockout Catch Basin 24”x30”x36” Tall, 8” W/F | 9
| WO15552 | Boxes | 2026-07-16 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208 | 105 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 29" | 1
| WO15241 | Boxes | 2026-07-16 | Core & Main LP (BG) #113 | Sales Order #23-2309 | 22 ST-SCI | BX2424-08BA36 | 24" x 24" - BOX BASE 8inW- 8inF - 36" | 1
| WO15240 | Boxes | 2026-07-16 | Core & Main LP (BG) #113 | Sales Order #23-2309 | 21 ST-SCI | BX2424-08BA30 | 24" x 24" - BOX BASE 8inW- 8inF - 30" | 1
| WO15230 | Boxes | 2026-07-16 | Core & Main LP (BG) #113 | Sales Order #23-2309 | 06 ST-SCI | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht - 25" | 1
| WO14947 | Boxes | 2026-07-16 | Josh King Excavation, LLC | Sales Order #25-2284C | D5 | BX3030-06RSVF | 30" x 30" - BOX RISER 6inW- Variable Ht F/F - 21" | 1
| WO14946 | Boxes | 2026-07-16 | Josh King Excavation, LLC | Sales Order #25-2284C | D1.1 QL5 | BX2828-06R42 | 28" x 28" - BOX RISER 6inW T/F - 42" | 1
| WO14702 | Boxes | 2026-07-16 | Eaton Asphalt | Sales Order #25-3193P2 | 500 | BX3636-08BAVF | "36"" x 36"" - BOX BASE 8inW- 8inF- Variable Ht F/n - 28""" | 1
| WO14684 | Boxes | 2026-07-16 | Eaton Asphalt | Sales Order #25-3193P2 | 520 | BX2436-08BVF | "24"" x 36"" - BOX BASE 8inW- 8inF- Variable Ht T/n - 47""" | 1
| WO14518 | Boxes | 2026-07-16 | Scotty's Contracting & Stone, LLC | Sales Order #25-3062P3 | CB-28 | BX3232-08BAVF | 32" x 32" - BOX BASE 8inW- 8inF- Variable Ht - 41" | 1
| WO14321 | Boxes | 2026-07-16 | Bear Construction, LLC | Sales Order #25-1401 | R25 | BX2828-06BA42 | 28" x 28" - BOX BASE 6inW- 6inF F/n - 42" | 1
| WO14222 | Boxes | 2026-07-16 | Louisville Paving and Construction | Sales Order #25-2952P3 | 131 | BX18180606VF | 18" x 18" - BOX BASE 6inW- 6inF- Variable Ht T/n - 20" | 1
| WO13881 | Boxes | 2026-07-16 | Jim Smith Contracting Co, LLC | Sales Order #26-2030 | 157+46 S4 DBI5D | BX3648-08BAVF | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht F/n - 31" | 1
| WO14274 | Boxes | 2026-07-16 | Louisville Paving and Construction | Sales Order #25-2952P3 | 145 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 37" | 1
| WO13766 | Boxes | 2026-07-16 | Hayes Pipe Supply | Sales Order #26-2310 | A1 ST-DCI | BX2864-06BA36 | 28" x 64" - BOX BASE 6inW- 6inF - 36" | 1
| WO15769 | GR | 2026-07-16 | Stock |  |  | GR30x30x6x3 |  | 1
| WO15766 | HW | 2026-07-16 | Stock |  |  | HWSF24 |  | 1
| WO15765 | HW | 2026-07-16 | Stock |  |  | HWPC36 |  | 1
| WO15764 | HW | 2026-07-16 | Stock |  |  | HWSF12 |  | 1
| WO15745 | HW | 2026-07-16 | Double A Services, Inc. | Sales Order #26-2989 | QL3 HW | HWSF18 | End Treatment 18" Sloped/Flared HW | 1
| WO15763 | JW | 2026-07-16 | Stock |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  | 2
| WO15760 | KYTC CBI | 2026-07-16 | Eaton Asphalt | Sales Order #25-3193P2 | 513 | CBITA10-BL | "24"" x 120"" - CB INLET KY A 10' BOTTOM LEFT T/G - 18""" | 1
| WO15759 | KYTC CBI | 2026-07-16 | Eaton Asphalt | Sales Order #25-3193P2 | 513 | CBITA10-TL | "24"" x 120"" - CB INLET KY A 10' TOP LEFT F/G - 10""" | 1
| WO15770 | RCP | 2026-07-16 | Stock |  |  | piprcp213 |  | 8
| WO15698 | RET | 2026-07-16 | Stock |  |  | RET-SS-MID-CAP |  | 1
| WO15697 | RET | 2026-07-16 | Stock |  |  | RET-SS-6-28-CG |  | 2
| WO15696 | RET | 2026-07-16 | Stock |  |  | RET-SS-24-44T-CG |  | 1
| WO15695 | RET | 2026-07-16 | Stock |  |  | RET-SS-24-86-CG |  | 4
| WO15694 | RET | 2026-07-16 | Stock |  |  | RET-SS-24-44-CG |  | 3
| WO15693 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-PARCP |  | 1
| WO15692 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-PAR-BC |  | 2
| WO15691 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-PAR-BC |  | 1
| WO15690 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-96-BC |  | 4
| WO15689 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-84-BC |  | 4
| WO15688 | RET | 2026-07-16 | Stock |  |  | RET-FORIX-30-BC |  | 33
| WO15350 | BC | 2026-07-16 | Eaton Asphalt | Sales Order #26-2254 | Box Culvert | BC168144-12W12T12F-12H | 168" x 144" - BOX CULVERT (12W/12F/12T) T/G - 69" | 1
| WO13328 | BC | 2026-07-16 | Jim Smith Contracting Co, LLC | Sales Order #24-1643B | St. 45+00 (PC 8) | BC048048-08WLF-9H | 48" x 48" - BOX CULVERT (08W/08F/08T) G/T - 69" | 1
| WO13320 | BC | 2026-07-16 | Jim Smith Contracting Co, LLC | Sales Order #24-1643B | St. 43+62 (PC 24) | BC096072-08WLF-9HC | 96" x 72" - BOX CULVERT (08W/08F/08T) No Groove F/T - 45" | 1
| WO15530 | Symon | 2026-07-16 | Barton Malow Company | Sales Order #26-1487P5 | 48x48 TOP SLAB w HOE-595 | CTS | 36" x 36" - CUST. TOP SLAB 6"W w/HOE-595 F/G F/F - 8" | 1
| WO15454 | Symon | 2026-07-16 | Pace Contracting, LLC | Sales Order #25-4444 | 54444 (2) | BX120120-08LD08SP | 120" x 120" - BX FLAT LID 8inW w/72"x84" HATCH - 8" | 1
| WO14948 | Symon | 2026-07-16 | Josh King Excavation, LLC | Sales Order #25-2284C | D2 | BX2896-06RVF | 28" x 96" - BOX RISER 6inW- Variable Ht F/F - 38" | 1
| WO13899 | Symon | 2026-07-16 | Jim Smith Contracting Co, LLC | Sales Order #26-2030 | 151+99 S-7 ST-JB | BX048084-08LD08S | 48" x 84" - BX FLAT LID 8inW SOLID F/F - 8" | 1
| WO09122 | Symon | 2026-07-16 | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | Secondary Pour | SECONDARY POUR - Add Exterior Drop to Base (P1) | 1
| WO12791 | Boxes | 2026-07-16 | Connhurst, LLC | Sales Order #26-1038 | 61038 (7) | BX6072-08BAVF-EB | 60" x 72" - BX BASE w/FLANGE 08W/08F/06EF F/n - 64" | 1
| WO12784 | Boxes | 2026-07-16 | Connhurst, LLC | Sales Order #26-1038 | 61038 (6) | BX060096-08LD08SP | 60" x 96" - BX FLAT LID 8"W w/36"x36" HATCH F/F - 8" | 1
| WO15475 | Symon | 2026-07-16 | Bowling Green Winsupply | Sales Order #26-3001 | GT 2 | Secondary Pour | SECONDARY POUR - Baffle Wall | 1

## WorkOrderProductionScheduleRes
Internal ID | Document Number | Status | WO Form ID | Start Date | End Date | Form ID | Customer | SO# | Structure # | Item | Description | Concrete Weight | Quantity | Stack-It PART - DrawingImage | QR Label | Submittal Drawing link | Scheduling Method | Expected Ship Date
101.0 | WO14020 | Released | 144MH | 2026-07-16 | 2026-07-21 | 144MH | Contech Engineered Solutions | Sales Order #26-2692 | 10-CS-12 | MH144RSVF | 144" - MH RISER Custom Ht T/G - 64" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2692%2520868541%2520Georgetown%2520Commons%2520Phase%25202%2520-%25202026060138/26-2692%252010-CS-12%2520P3%2520MH144RSVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2692%2520868541%2520Georgetown%2520Commons%2520Phase%25202%2520-%25202026060138/26-2692%252010-CS-12%2520P3%2520MH144RSVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2692%2520868541%2520Georgetown%2520Commons%2520Phase%25202%2520-%25202026060138/26-2692%252010-CS-12%2520Submittal.pdf
101.0 | WO15519 | Released | 36MH | 2026-07-16 | 2026-07-21 | 36MH | ADS Advanced Drainage Systems, Inc. | Sales Order #26-2604 | AR3PC | MH036RS18 | 36" - MH RISER T/G - 18" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2604%2520ADS%2520Abound%2520Credit%2520Union%2520-%25202026060218/26-2604%2520AR3PC%2520P3%2520MH036RS18%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2604%2520ADS%2520Abound%2520Credit%2520Union%2520-%25202026060218/26-2604%2520AR3PC%2520P3%2520MH036RS18%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2604%2520ADS%2520Abound%2520Credit%2520Union%2520-%25202026060218/26-2604%2520AR3PC%2520Submittal.pdf
| WO15771 | Released | 48MH | 2026-07-16 | 2026-07-17 | 48MH | Stock |  |  | MH048RS36 |  |  | 2
| WO15768 | Released | 48MH | 2026-07-16 | 2026-07-17 | 48MH | Stock |  |  | MH048CN36 |  |  | 2
| WO15767 | Released | 48MH | 2026-07-16 | 2026-07-17 | 48MH | Stock |  |  | MH048LD07C |  |  | 3
| WO15756 | Released | 48MH | 2026-07-16 | 2026-07-16 | 48MH | Stock |  |  | MH048LD12-24X36RECT |  |  | 2
101.0 | WO15749 | Released | 48MH | 2026-07-16 | 2026-07-22 | 48MH | Contech Engineered Solutions | Sales Order #26-2920 | 10-CS-4 | MH048RS24 | 48" - MH RISER T/G - 24" | 0.43015 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520P3%2520MH048RS24%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520P3%2520MH048RS24%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520Submittal.pdf
101.0 | WO15746 | Released | 48MH | 2026-07-16 | 2026-07-22 | 48MH | Contech Engineered Solutions | Sales Order #26-2920 | 10-CS-4 | MH048BA18 | 48" - MH BASE T/n - 18" | 0.66432 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520P1%2520MH048BA18%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520P1%2520MH048BA18%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2920%2520853382%2520Urgent%2520Care%2520-%25202026070018/26-2920%252010-CS-4%2520Submittal.pdf
1.0 | WO15734 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Hayes Pipe Supply | Sales Order #26-2310P2 | MH 082-09-371 SS-MH | MH048BA24CDARED | 48" - MH BASE w/ConBlock-CDA Red - 24" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520P1%2520MH048BA24CDARED%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520P1%2520MH048BA24CDARED%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520Submittal.pdf
1.0 | WO15733 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Hayes Pipe Supply | Sales Order #26-2310P2 | MH 082-09-371 SS-MH | MH048LD12SCDARED | 48" - MH FLAT TOP w/32" Hole CC w/ConBlock-CDA Red - 12" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520P2%2520MH048LD12SCDARED%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520P2%2520MH048LD12SCDARED%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520MH%2520082-09-371%2520SS-MH%2520Submittal.pdf
| WO15663 | Released | 48MH | 2026-07-16 | 2026-07-17 | 48MH | Cumberland Pipeline LLC | Sales Order #25-4288P2 | A3 | MH048RS72X | 48" - MH RISER w/XYPEX - 72" | 1.2915 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4288%2520-%2520Project%2520Wave%2520-%2520202606003M/25-4288%2520A3%2520P4%2520MH048RS72X%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4288%2520-%2520Project%2520Wave%2520-%2520202606003M/25-4288%2520A3%2520P4%2520MH048RS72X%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4288%2520-%2520Project%2520Wave%2520-%2520202606003M/25-4288%2520A3%2520Submittal.pdf
101.0 | WO15423 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Contech Engineered Solutions | Sales Order #26-2877 | 20-CS-4 | MH048LD12-30 | 48" - MH FLAT LID w/30in ECC Hole F/G - 12" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520P3%2520MH048LD12-30%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520P3%2520MH048LD12-30%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520Submittal.pdf
101.0 | WO15395 | Released | 48MH | 2026-07-16 | 2026-07-21 | 48MH | Contech Engineered Solutions | Sales Order #26-2877 | 20-CS-4 | MH048RS72S | 48" - MH RISER SPECIAL T/G - 72" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520P2%2520MH048RS72S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520P2%2520MH048RS72S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2877%2520839248%2520Aloft%2520-%25202026060308/26-2877%252020-CS-4%2520Submittal.pdf
102.0 | WO15071 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Citco Water | Sales Order #25-4212P3 | A11 REV.A | MH048CN24-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 24" | 0.44623 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4212%2520-%2520Greentree%2520Lane%2520Sewer%2520-%2520202511007H/A11%2520REV.A%2520P3%2520MH048CN24-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4212%2520-%2520Greentree%2520Lane%2520Sewer%2520-%2520202511007H/A11%2520REV.A%2520P3%2520MH048CN24-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4212%2520-%2520Greentree%2520Lane%2520Sewer%2520-%2520202511007H/A11%2520REV.A%2520Submittal.pdf
33.0 | WO14326 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Bear Construction, LLC | Sales Order #25-1401 | R29A | MH048INV14G | 48" - STORM INVERT CHANNEL - 1/4 HEIGHT | 1.003 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R29A%2520Submittal.pdf
15.0 | WO13790 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Hayes Pipe Supply | Sales Order #26-2310 | PMH2 SS-MH | MH048INVFCDARED | 48" - MH INVERT CHANNEL w/ConBlock-CDA Red - FULL HEIGHT | 1 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520PMH2%2520SS-MH%2520Submittal.pdf
13.0 | WO13787 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Hayes Pipe Supply | Sales Order #26-2310 | PMH1 SS-MH | MH048INVFCDARED | 48" - MH INVERT CHANNEL w/ConBlock-CDA Red - FULL HEIGHT | 1 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520PMH1%2520SS-MH%2520Submittal.pdf
13.0 | WO13785 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Hayes Pipe Supply | Sales Order #26-2310 | PMH1 SS-MH | MH048CCN36CDARED | 48" - CON CONE w/24" HOLE- w/ConBlock-CDA Red - 36" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520PMH1%2520SS-MH%2520P2%2520MH048CCN36CDARED%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520PMH1%2520SS-MH%2520P2%2520MH048CCN36CDARED%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520PMH1%2520SS-MH%2520Submittal.pdf
8.0 | WO13400 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1.003 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520Submittal.pdf
8.0 | WO13398 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048RS60S | 48" - MH RISER NO STEPS - 60" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520P2%2520MH048RS60S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520P2%2520MH048RS60S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520Submittal.pdf
8.0 | WO13397 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A5 (9) | MH048CN42-S | 48" - ECC CONE w/ 24" HOLE NO STEP - 42" | 0.8 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520P3%2520MH048CN42-S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520P3%2520MH048CN42-S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A5%2520%25289%2529%2520Submittal.pdf
7.0 | WO13396 | Released | 48MH | 2026-07-16 | 2026-07-20 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A4 (8) | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1.003 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A4%2520%25288%2529%2520Submittal.pdf
1.0 | WO15576 | Released | 60MH | 2026-07-16 | 2026-07-21 | 60MH | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | SCUM WW | MH060BAEVF | 60" - MH BASE w/FLANGE (08F/07EF) - 43" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520WW%2520P1%2520MH060BAEVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520WW%2520P1%2520MH060BAEVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520WW%2520Submittal.pdf
43.0 | WO14360 | Released | 60MH | 2026-07-16 | 2026-07-20 | 60MH | Bear Construction, LLC | Sales Order #25-1401 | R44 | MH060INV14G | 60" - STORM INVERT CHANNEL - 1/4 HEIGHT | 1.003 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R44%2520Submittal.pdf
43.0 | WO14358 | Released | 60MH | 2026-07-16 | 2026-07-20 | 60MH | Bear Construction, LLC | Sales Order #25-1401 | R44 | MH060LD08SP | 60" - MH FLAT TOP - TDOT D-RJB-1 (SOLID) F/F - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R44%2520P2%2520MH060LD08SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R44%2520P2%2520MH060LD08SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R44%2520Submittal.pdf
162.0 | WO09210 | Released | 60MH | 2026-07-16 | 2026-07-22 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301560 | MH060DPVF | 60" - MH BASE (10"F) w/DROP Custom Ht T/n - 62" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301560%2520P1%2520MH060DPVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301560%2520P1%2520MH060DPVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301560%2520Submittal.pdf
161.0 | WO09119 | Released | 60MH | 2026-07-16 | 2026-07-20 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | MH060RSVF-D | 60" - MH RISER w/DROP Custom Ht T/G - 52" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520P2%2520MH060RSVF-D%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520P2%2520MH060RSVF-D%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520Submittal.pdf
161.0 | WO09118 | Released | 60MH | 2026-07-16 | 2026-07-20 | 60MH | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | MH060TS15-48ECC | 60" - MH Transition Slab 48" Hole T/G - 15" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520P3%2520MH060TS15-48ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520P3%2520MH060TS15-48ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3118%2520-%2520W6%2520Ph%25202-C%2520Force%2520Main%2520Improvements%2520-%2520202512007N/25-3118%25202301559%2520Submittal.pdf
3.0 | WO13556 | Released | 84MH | 2026-07-16 | 2026-07-22 | 84MH | Pace Contracting, LLC | Sales Order #25-4547 | PROCESS RETURN P.S. | MH084LD17SP | 84" - MH FLAT TOP w/48"x60" Hatch - 17" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520P.S.%2520P4%2520MH084LD17SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520P.S.%2520P4%2520MH084LD17SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520PROCESS%2520RETURN%2520P.S.%2520Submittal.pdf
1.0 | WO15350 | Released | BC | 2026-07-16 | 2026-07-21 | BC | Eaton Asphalt | Sales Order #26-2254 | Box Culvert | BC168144-12W12T12F-12H | 168" x 144" - BOX CULVERT (12W/12F/12T) T/G - 69" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2254%2520-%2520Wilder%2520Box%2520Culvert%2520-%2520202606004M/26-2254%2520Box%2520Culvert%2520P25%2520BC168144-12W12T12F-12H%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2254%2520-%2520Wilder%2520Box%2520Culvert%2520-%2520202606004M/26-2254%2520Box%2520Culvert%2520P25%2520BC168144-12W12T12F-12H%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2254%2520-%2520Wilder%2520Box%2520Culvert%2520-%2520202606004M/26-2254%2520Box%2520Culvert%2520Submittal.pdf
2.0 | WO13328 | Released | BC | 2026-07-16 | 2026-07-17 | BC | Jim Smith Contracting Co, LLC | Sales Order #24-1643B | St. 45+00 (PC 8) | BC048048-08WLF-9H | 48" x 48" - BOX CULVERT (08W/08F/08T) G/T - 69" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252045%252B00%2520%2528PC%25208%2529%2520P1%2520BC048048-08WLF-9H%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252045%252B00%2520%2528PC%25208%2529%2520P1%2520BC048048-08WLF-9H%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252045%252B00%2520%2528PC%25208%2529%2520Submittal.pdf
1.0 | WO13320 | Released | BC | 2026-07-16 | 2026-07-17 | BC | Jim Smith Contracting Co, LLC | Sales Order #24-1643B | St. 43+62 (PC 24) | BC096072-08WLF-9HC | 96" x 72" - BOX CULVERT (08W/08F/08T) No Groove F/T - 45" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252043%252B62%2520%2528PC%252024%2529%2520P1%2520BC096072-08WLF-9HC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252043%252B62%2520%2528PC%252024%2529%2520P1%2520BC096072-08WLF-9HC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-1643B%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520200%2520%2528ID%2520241301%2529%2520-%25202026020021/24-1643B%2520St.%252043%252B62%2520%2528PC%252024%2529%2520Submittal.pdf
1.0 | WO15744 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Double A Services, Inc. | Sales Order #26-2989 | QL1 DBI13G | BX2430-08B36-KO | Knockout Catch Basin 24”x30”x36” Tall, 8” W/F | 6.3498 | 9
102.0 | WO15552 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208 | 105 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 29" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520105%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520105%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520105%2520Submittal.pdf
14.0 | WO15241 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Core & Main LP (BG) #113 | Sales Order #23-2309 | 22 ST-SCI | BX2424-08BA36 | 24" x 24" - BOX BASE 8inW- 8inF - 36" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252022%2520ST-SCI%2520P1%2520BX2424-08BA36%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252022%2520ST-SCI%2520P1%2520BX2424-08BA36%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252022%2520ST-SCI%2520Submittal.pdf
13.0 | WO15240 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Core & Main LP (BG) #113 | Sales Order #23-2309 | 21 ST-SCI | BX2424-08BA30 | 24" x 24" - BOX BASE 8inW- 8inF - 30" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252021%2520ST-SCI%2520P1%2520BX2424-08BA30%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252021%2520ST-SCI%2520P1%2520BX2424-08BA30%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252021%2520ST-SCI%2520Submittal.pdf
4.0 | WO15230 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Core & Main LP (BG) #113 | Sales Order #23-2309 | 06 ST-SCI | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht - 25" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252006%2520ST-SCI%2520P1%2520BX2424-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252006%2520ST-SCI%2520P1%2520BX2424-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/23-2309%2520-%2520Richland%2520Estates%2520Subdivision%2520-%25202026040061/23-2309%252006%2520ST-SCI%2520Submittal.pdf
8.0 | WO14947 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Josh King Excavation, LLC | Sales Order #25-2284C | D5 | BX3030-06RSVF | 30" x 30" - BOX RISER 6inW- Variable Ht F/F - 21" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D5%2520P1%2520BX3030-06RSVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D5%2520P1%2520BX3030-06RSVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D5%2520Submittal.pdf
7.0 | WO14946 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Josh King Excavation, LLC | Sales Order #25-2284C | D1.1 QL5 | BX2828-06R42 | 28" x 28" - BOX RISER 6inW T/F - 42" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D1.1%2520QL5%2520P1%2520BX2828-06R42%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D1.1%2520QL5%2520P1%2520BX2828-06R42%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D1.1%2520QL5%2520Submittal.pdf
109.0 | WO14702 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Eaton Asphalt | Sales Order #25-3193P2 | 500 | BX3636-08BAVF | "36"" x 36"" - BOX BASE 8inW- 8inF- Variable Ht F/n - 28""" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520500%2520P1%2520BX3636-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520500%2520P1%2520BX3636-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520500%2520Submittal.pdf
155.0 | WO14684 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Eaton Asphalt | Sales Order #25-3193P2 | 520 | BX2436-08BVF | "24"" x 36"" - BOX BASE 8inW- 8inF- Variable Ht T/n - 47""" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520520%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520520%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520520%2520Submittal.pdf
128.0 | WO14518 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #25-3062P3 | CB-28 | BX3232-08BAVF | 32" x 32" - BOX BASE 8inW- 8inF- Variable Ht - 41" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3062%2520Portland%2520Bypass%2520-%25202025100078/25-3062%2520CB-28%2520P1%2520BX3232-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3062%2520Portland%2520Bypass%2520-%25202025100078/25-3062%2520CB-28%2520P1%2520BX3232-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3062%2520Portland%2520Bypass%2520-%25202025100078/25-3062%2520CB-28%2520Submittal.pdf
27.0 | WO14321 | Released | Boxes | 2026-07-16 | 2026-07-20 | Boxes | Bear Construction, LLC | Sales Order #25-1401 | R25 | BX2828-06BA42 | 28" x 28" - BOX BASE 6inW- 6inF F/n - 42" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R25%2520P1%2520BX2828-06BA42%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R25%2520P1%2520BX2828-06BA42%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R25%2520Submittal.pdf
165.0 | WO14222 | Released | Boxes | 2026-07-16 | 2026-07-17 | Boxes | Louisville Paving and Construction | Sales Order #25-2952P3 | 131 | BX18180606VF | 18" x 18" - BOX BASE 6inW- 6inF- Variable Ht T/n - 20" | 0.11658 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520131%2520P1%2520BX18180606VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520131%2520P1%2520BX18180606VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520131%2520Submittal.pdf
119.0 | WO13881 | Released | Boxes | 2026-07-16 | 2026-07-17 | Boxes | Jim Smith Contracting Co, LLC | Sales Order #26-2030 | 157+46 S4 DBI5D | BX3648-08BAVF | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht F/n - 31" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520157%252B46%2520S4%2520DBI5D%2520P1%2520BX3648-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520157%252B46%2520S4%2520DBI5D%2520P1%2520BX3648-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520157%252B46%2520S4%2520DBI5D%2520Submittal.pdf
5.0 | WO12791 | Released | Boxes | 2026-07-16 | 2026-07-17 | Boxes | Connhurst, LLC | Sales Order #26-1038 | 61038 (7) | BX6072-08BAVF-EB | 60" x 72" - BX BASE w/FLANGE 08W/08F/06EF F/n - 64" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25287%2529%2520P1%2520BX6072-08BAVF-EB%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25287%2529%2520P1%2520BX6072-08BAVF-EB%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25287%2529%2520Submittal.pdf
4.0 | WO12784 | Released | Boxes | 2026-07-16 | 2026-07-17 | Boxes | Connhurst, LLC | Sales Order #26-1038 | 61038 (6) | BX060096-08LD08SP | 60" x 96" - BX FLAT LID 8"W w/36"x36" HATCH F/F - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25286%2529%2520P2%2520BX060096-08LD08SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25286%2529%2520P2%2520BX060096-08LD08SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1038%2520-%2520Perryville%2520-%2520Junction%2520City%2520WW%2520Improvements%2520-%2520202602005M/26-1038%252061038%2520%25286%2529%2520Submittal.pdf
26.0 | WO14320 | Released | FES | 2026-07-16 | 2026-07-17 | FES | Bear Construction, LLC | Sales Order #25-1401 | R23 | DRAINSLOPE | 28" x 28" - STORM INVERT CHANNEL (FLAT) - 4" THK | 1.003 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1401%2520Irwin%2520Landing%2520Ph-%25201%2520-%25202026030268/25-1401%2520R23%2520Submittal.pdf
| WO15769 | Released | GR | 2026-07-16 | 2026-07-17 | GR | Stock |  |  | GR30x30x6x3 |  |  | 1
| WO15766 | Released | HW | 2026-07-16 | 2026-07-16 | HW | Stock |  |  | HWSF24 |  |  | 1
| WO15765 | Released | HW | 2026-07-16 | 2026-07-16 | HW | Stock |  |  | HWPC36 |  |  | 1
| WO15764 | Released | HW | 2026-07-16 | 2026-07-16 | HW | Stock |  |  | HWSF12 |  |  | 1
6.0 | WO15745 | Released | HW | 2026-07-16 | 2026-07-20 | HW | Double A Services, Inc. | Sales Order #26-2989 | QL3 HW | HWSF18 | End Treatment 18" Sloped/Flared HW | 0.93467 | 1
| WO15763 | Released | JW | 2026-07-16 | 2026-07-21 | JW | Stock |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  |  | 1
118.0 | WO15760 | Released | KYTC CBI | 2026-07-16 | 2026-07-20 | KYTC CBI | Eaton Asphalt | Sales Order #25-3193P2 | 513 | CBITA10-BL | "24"" x 120"" - CB INLET KY A 10' BOTTOM LEFT T/G - 18""" | 1 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520513%2520Submittal.pdf
118.0 | WO15759 | Released | KYTC CBI | 2026-07-16 | 2026-07-20 | KYTC CBI | Eaton Asphalt | Sales Order #25-3193P2 | 513 | CBITA10-TL | "24"" x 120"" - CB INLET KY A 10' TOP LEFT F/G - 10""" | 0.5 | 1 |  |  | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520513%2520Submittal.pdf
| WO15770 | Released | RCP | 2026-07-16 | 2026-07-17 | RCP | Stock |  |  | piprcp213 |  |  | 8
| WO15698 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-SS-MID-CAP |  |  | 1
| WO15697 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-SS-6-28-CG |  |  | 2
| WO15696 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-SS-24-44T-CG |  |  | 1
| WO15695 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-SS-24-86-CG |  |  | 4
| WO15694 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-SS-24-44-CG |  |  | 3
| WO15693 | Released | RET | 2026-07-16 | 2026-07-17 | RET | Stock |  |  | RET-FORIX-PARCP |  |  | 1
| WO15692 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-FORIX-PAR-BC |  |  | 2
| WO15691 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-FORIX-PAR-BC |  |  | 1
| WO15690 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-FORIX-96-BC |  |  | 4
| WO15689 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-FORIX-84-BC |  |  | 4
| WO15688 | Released | RET | 2026-07-16 | 2026-07-16 | RET | Stock |  |  | RET-FORIX-30-BC |  |  | 33
1.0 | WO15530 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Barton Malow Company | Sales Order #26-1487P5 | 48x48 TOP SLAB w HOE-595 | CTS | 36" x 36" - CUST. TOP SLAB 6"W w/HOE-595 F/G F/F - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1487%2520-%2520Ford%2520LAP%2520-%25202026030051/26-1487%252048x48%2520TOP%2520SLAB%2520w%2520HOE-595%2520P1%2520CTS%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1487%2520-%2520Ford%2520LAP%2520-%25202026030051/26-1487%252048x48%2520TOP%2520SLAB%2520w%2520HOE-595%2520P1%2520CTS%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1487%2520-%2520Ford%2520LAP%2520-%25202026030051/26-1487%252048x48%2520TOP%2520SLAB%2520w%2520HOE-595%2520Submittal.pdf
2.0 | WO15475 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Bowling Green Winsupply | Sales Order #26-3001 | GT 2 | Secondary Pour | SECONDARY POUR - Baffle Wall | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3001%2520-%2520Gunnison%2520Way%2520Grease%2520Traps%2520-%25202026070024/26-3001%2520GT%25202%2520P1%2520BX60120-06W06F-BA54%2520Shop.pdf
1.0 | WO15454 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Pace Contracting, LLC | Sales Order #25-4444 | 54444 (2) | BX120120-08LD08SP | 120" x 120" - BX FLAT LID 8inW w/72"x84" HATCH - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4444%2520-%2520Downtown%2520WWTP%2520Wet%2520Weather%2520Screening%2520-%2520202602007Q/25-4444%252054444%2520%25282%2529%2520P3%2520BX120120-08LD08SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4444%2520-%2520Downtown%2520WWTP%2520Wet%2520Weather%2520Screening%2520-%2520202602007Q/25-4444%252054444%2520%25282%2529%2520P3%2520BX120120-08LD08SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4444%2520-%2520Downtown%2520WWTP%2520Wet%2520Weather%2520Screening%2520-%2520202602007Q/25-4444%252054444%2520%25282%2529%2520Submittal.pdf
9.0 | WO14948 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Josh King Excavation, LLC | Sales Order #25-2284C | D2 | BX2896-06RVF | 28" x 96" - BOX RISER 6inW- Variable Ht F/F - 38" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D2%2520P1%2520BX2896-06RVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D2%2520P1%2520BX2896-06RVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284C%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026060198/25-2284C%2520D2%2520Submittal.pdf
109.0 | WO14274 | Released | Symon | 2026-07-16 | 2026-07-21 | Symon | Louisville Paving and Construction | Sales Order #25-2952P3 | 145 | BX2424-08BAVF | 24" x 24" - BOX BASE 8inW- 8inF- Variable Ht F/n - 37" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520145%2520P1%2520BX2424-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520145%2520P1%2520BX2424-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2952%2520-%2520KYTC%2520Jefferson%2520Co%2520Call%2520106%2520%2528251315%2529%2520-%2520202512003N/25-2952%2520145%2520Submittal.pdf
118.0 | WO13899 | Released | Symon | 2026-07-16 | 2026-07-17 | Symon | Jim Smith Contracting Co, LLC | Sales Order #26-2030 | 151+99 S-7 ST-JB | BX048084-08LD08S | 48" x 84" - BX FLAT LID 8inW SOLID F/F - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520151%252B99%2520S-7%2520ST-JB%2520P2%2520BX048084-08LD08S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520151%252B99%2520S-7%2520ST-JB%2520P2%2520BX048084-08LD08S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2030%2520-%2520KYTC%2520McCracken%2520Co-%2520Call%2520111%2520%2528ID%2520264505%2529%2520-%25202026050111/26-2030%2520151%252B99%2520S-7%2520ST-JB%2520Submittal.pdf
3.0 | WO13766 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Hayes Pipe Supply | Sales Order #26-2310 | A1 ST-DCI | BX2864-06BA36 | 28" x 64" - BOX BASE 6inW- 6inF - 36" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520A1%2520ST-DCI%2520P1%2520BX2864-06BA36%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520A1%2520ST-DCI%2520P1%2520BX2864-06BA36%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-2310%2520-%25203rd%2520-%2520Madison%2520Townhomes%2520-%2520Ph-%25201%2520-%2520202605004T/26-2310%2520A1%2520ST-DCI%2520Submittal.pdf
11.0 | WO13280 | Released | Symon | 2026-07-16 | 2026-07-22 | Symon | Endesol, Inc. | Sales Order #26-1355 | Lift Station | CTRS-X | 72" - Combined Lift Station Walls/Floor w/XYPEX - 71" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1355%2520Sinking%2520Creek%2520Rd%2520Sanitary%2520Sewer%2520Ext-%2520Ph-%25202%2520-%25202026040018/26-1355%2520Lift%2520Station%2520P3%2520CTRS-X%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1355%2520Sinking%2520Creek%2520Rd%2520Sanitary%2520Sewer%2520Ext-%2520Ph-%25202%2520-%25202026040018/26-1355%2520Lift%2520Station%2520P3%2520CTRS-X%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1355%2520Sinking%2520Creek%2520Rd%2520Sanitary%2520Sewer%2520Ext-%2520Ph-%25202%2520-%25202026040018/26-1355%2520Lift%2520Station%2520Submittal.pdf
161.0 | WO09122 | Released | Symon | 2026-07-16 | 2026-07-20 | Symon | Lykins Contracting LLC | Sales Order #25-3118 | 2301559 | Secondary Pour | SECONDARY POUR - Add Exterior Drop to Base (P1) | 1.003 | 1