## Shop Schedule
Completed | Document Number | WO Form ID | Start Date | Customer | SO# | Structure # | Item | Description | Quantity
| WO18145 | 36MH | 2026-08-20 | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-23 | MH036RSVF | 36" - MH RISER Custom Ht F/G - 62" | 1
| WO18259 | 48MH | 2026-08-20 |  |  |  | MH048RSVF |  | 1
| WO18258 | 48MH | 2026-08-20 |  |  |  | MH048RSVF |  | 1
| WO18257 | 48MH | 2026-08-20 |  |  |  | MH048RS72 |  | 1
| WO18252 | 48MH | 2026-08-20 |  |  |  | MH048LD12ECC |  | 1
| WO18251 | 48MH | 2026-08-20 |  |  |  | MH048BA48-B |  | 1
| WO18250 | 48MH | 2026-08-20 |  |  |  | MH048RS36 |  | 1
| WO18249 | 48MH | 2026-08-20 |  |  |  | MH048RS48 |  | 2
| WO18201 | 48MH | 2026-08-20 | Pace Contracting, LLC | Sales Order #25-4547P2 | MH-39-01A | MH048RS24 | 48" - MH RISER - 24" | 1
| WO18188 | 48MH | 2026-08-20 | Connhurst, LLC | Sales Order #26-1066 | A6 (10) | MH048LD12ECC | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 1
| WO18131 | 48MH | 2026-08-20 |  |  |  | MH048CN36 |  | 2
| WO18062 | 48MH | 2026-08-20 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL12 SS-MH | MH048BA42 | 48" - MH BASE - 42" | 1
| WO18059 | 48MH | 2026-08-20 | Luttrell & Sons, LLC | Sales Order #26-1814 | 0+68 SS-MH | MH048BA18 | 48" - MH BASE - 18" | 1
| WO18058 | 48MH | 2026-08-20 | Luttrell & Sons, LLC | Sales Order #26-1814 | 0+68 SS-MH | MH048RS72S | 48" - MH RISER SPECIAL - 72" | 1
| WO15601 | 48MH | 2026-08-20 | Cumberland Pipeline LLC | Sales Order #25-4288P2 | A13 | MH048INVFX | 48" - MH INVERT CHANNEL w/XYPEX - FULL HEIGHT | 1
| WO13415 | 48MH | 2026-08-20 | Connhurst, LLC | Sales Order #26-1066 | 44+80 AR (14) | MH048LD12S | 48" - MH FLAT TOP w/30"x36" Hatch - 12" | 1
| WO13410 | 48MH | 2026-08-20 | Connhurst, LLC | Sales Order #26-1066 | 20+49.85 AR (14) | MH048LD12S | 48" - MH FLAT TOP w/30"x36" Hatch - 12" | 1
| WO11841 | 48MH | 2026-08-20 | Citco Water |  | 77+93 ARV | MH048CN36 | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 2
| WO11732 | 48MH | 2026-08-20 |  |  |  | MH048CN30 |  | 2
| WO11476 | 48MH | 2026-08-20 |  |  |  | MH048CN42X |  | 1
| WO10405 | 48MH | 2026-08-20 | Cumberland Pipeline LLC | Sales Order #26-1322B | 246-87 SS-MH | MH048BAVF | 48" - MH BASE (08"F) T/n - 38" | 1
| WO10401 | 48MH | 2026-08-20 | Cumberland Pipeline LLC | Sales Order #26-1322B | 179-84 SS-MH | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1
| WO08015 | 48MH | 2026-08-20 |  |  |  | MH048BA36-KO |  | 1
| WO01970 | 48MH | 2026-08-20 | Lawrence Construction & Leasing, Inc. | Sales Order #25-1385C | 51385C 2-2 | MH048RSVF | 48" - MH RISER Custom Ht T/G - 36" | 1
| WO18205 | 60MH | 2026-08-20 | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060RS72 | 60" - MH RISER T/G - 72" | 1
| WO18204 | 60MH | 2026-08-20 | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060LD13-30ECC | 60" - MH FLAT TOP SPEC. (30" ECC HOLE) F/G - 13" | 1
| WO18202 | 60MH | 2026-08-20 | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060BA18 | 60" - MH BASE T/n - 18" | 1
| WO18198 | 60MH | 2026-08-20 | Hubert Excavating & Contracting | Sales Order #25-3579P6 | MH A11 Riser | MH060RSVFS | 60" - MH RISER Custom Ht- w/Coating T/G - 28" | 1
| WO18169 | 60MH | 2026-08-20 | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-14 | MH060LD13CC | 60" - MH FLAT TOP w/24" Ctr. Hole F/G - 13" | 1
| WO18260 | 72MH | 2026-08-20 |  |  |  | MH072TS15-48ECC |  | 1
| WO17416 | 84MH | 2026-08-20 | Garney Companies, Inc. | Sales Order #26-1549P2 | MH-3-4 SS-MH | MH084BAEVFX | 84" - MH BASE w/FLANGE (12F/14EF) w/XYPEX - 93" | 1
| WO18073 | 96MH | 2026-08-20 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL6 | MH096RS84 | 96" - MH RISER - 84" | 1
| WO18217 | BLK | 2026-08-20 |  |  |  | BLK242436AB |  | 1
| WO18212 | Boxes | 2026-08-20 |  |  |  | BX2424-06B30-KO |  | 1
| WO18211 | Boxes | 2026-08-20 |  |  |  | BX1818-06B24-KO |  | 1
| WO17921 | Boxes | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 272 (437+45 RT) | BX2436-08R36 | 24" x 36" - BOX RISER 8inW T/G - 36" | 1
| WO17920 | Boxes | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 272 (437+45 RT) | BX2436-08R36 | 24" x 36" - BOX RISER 8inW F/G - 36" | 1
| WO17900 | Boxes | 2026-08-20 | Convergent Water Technologies, Inc. | Sales Order #26-3166 | FB2 ST-DBI | BX4848-08BAVF | 48" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 1
| WO17808 | Boxes | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5088+83 RT CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 1
| WO17804 | Boxes | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5086+83 RT CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 1
| WO17746 | Boxes | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 262 (433+25 RT) | BX3648-08BA60 | 36" x 48" - BOX BASE 8inW- 8inF F/n - 60" | 1
| WO17710 | Boxes | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 238 (426+83 LT) | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 23" | 1
| WO17654 | Boxes | 2026-08-20 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 470 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 47" | 1
| WO17617 | Boxes | 2026-08-20 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 589 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 29" | 1
| WO17609 | Boxes | 2026-08-20 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 476 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 43" | 1
| WO18167 | FES | 2026-08-20 | Russell's Excavating | Sales Order #26-1227 | FES 24" TOE WALL | FES24B-TB | FLARED END SECTION BELL TOE BLOCK (OUTLET) | 1
| WO17903 | FES | 2026-08-20 | Cleary Construction, Inc. | Sales Order #26-1077P7 | B5 | DRAINSLOPE | 24" x 36" - STORM INVERT CHANNEL (FLAT) - 4" THK | 1
| WO14643 | FES | 2026-08-20 |  |  |  | FES12S |  | 1
| WO18255 | HW | 2026-08-20 |  |  |  | HWBW24F |  | 1
| WO18254 | HW | 2026-08-20 |  |  |  | HWSF15 |  | 1
| WO18253 | HW | 2026-08-20 |  |  |  | HWSF18 |  | 1
| WO15156 | HW | 2026-08-20 |  |  |  | HWPC42 |  | 1
| WO16552 | JW | 2026-08-20 |  |  |  | MBI-TCCB-10-JJ |  | 30
| WO16422 | JW | 2026-08-20 |  |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  | 4
| WO17839 | Symon | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 4016+80 LT CBBI-MOD A1 (Top Phase) | CMBBIT9-A1SG | 24" x 120" - CB MED BAR BOX INLET 9A1 SAG - 17" | 1
| WO17792 | KYTC MBI | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5080+02 RT CBBI-MOD B1 (Top Phase) | CMBBIT9-B1RH | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 1
| WO18206 | RCP | 2026-08-20 |  |  |  | PIPRCP214 |  | 16
| WO18190 | RCP | 2026-08-20 |  |  |  | PIPRCP663 |  | 8
| WO18226 | RET | 2026-08-20 |  |  |  | RET-FORIX-60-BC |  | 4
| WO18216 | RET | 2026-08-20 |  |  |  | RET-SS-6-44-CG |  | 2
| WO18215 | RET | 2026-08-20 |  |  |  | RET-SS-3SF-CG |  | 2
| WO16146 | RET | 2026-08-20 |  |  |  | RET-SS-MID-CAP |  | 1
| WO16145 | RET | 2026-08-20 |  |  |  | RET-SS-6-28-CG |  | 2
| WO16144 | RET | 2026-08-20 |  |  |  | RET-SS-24-44T-CG |  | 1
| WO16143 | RET | 2026-08-20 |  |  |  | RET-SS-24-86-CG |  | 4
| WO16142 | RET | 2026-08-20 |  |  |  | RET-SS-24-44-CG |  | 3
| WO16141 | RET | 2026-08-20 |  |  |  | RET-FORIX-PARCP |  | 1
| WO16140 | RET | 2026-08-20 |  |  |  | RET-FORIX-PAR-BC |  | 2
| WO16139 | RET | 2026-08-20 |  |  |  | RET-FORIX-PAR-BC |  | 1
| WO16136 | RET | 2026-08-20 |  |  |  | RET-FORIX-30-BC |  | 33
| WO17082 | Secondary Activity | 2026-08-20 | Contech Engineered Solutions | Sales Order #26-3104 | 10-KFPD0608 | PSASSEMBLY | ASSEMBLY REQUIRED | 1
| WO16980 | Secondary Activity | 2026-08-20 | Endesol, Inc. | Sales Order #26-3067 | QL1 ACC1 | Special Pre-Assembly | Special Pre-Assembly Of Internal Materials Required | 1
| WO18137 | Symon | 2026-08-20 | Josh King Excavation, LLC | Sales Order #25-2284D | L2 ST-TCI | BX2896-06BVF | 28" x 96" - BOX BASE 6inW- 6inF- Variable Ht F/n - 65" | 1
| WO17734 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 232 (424+73 RT) | BX024060-08LD08-1559 | 24" x 60" - BX FLAT LID 8inW- w/15"x59" HOLE (KYTC DBI-13S) F/F - 8" | 1
| WO18218 | Symon | 2026-08-20 | Louisville Paving and Construction | Sales Order #25-2952 | MSD HW | HWMSD12 | End Treatment 12" MSD Std. Straight Headwall | 1
| WO18121 | Symon | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5090+98 RT CBBI-MOD B1 | BX036036-08TS024036 | 36" x 36" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 1
| WO18108 | Symon | 2026-08-20 | Convergent Water Technologies, Inc. | Sales Order #26-1706 | QL1 | Secondary Pour | SECONDARY POUR - WEIR WALL | 1
| WO18075 | Symon | 2026-08-20 | Luttrell & Sons, LLC | Sales Order #26-1814 | QL6 | Secondary Pour | SECONDARY POUR - EXT. FLANGE | 1
| WO18035 | Symon | 2026-08-20 | Clarksville Gas & Water Dept. | Sales Order #26-1735 | QL2 | BX120120-08LD08SP | 120" x 120" - BX FLAT LID 8inW w/2x 42"x72" HATCHES - 8" | 1
| WO17959 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-19 | BX2436-06LD08-SP | 24" x 36" - BX FLAT LID 8inW w/24"x30" HOLE F/F - 6" | 1
| WO17948 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-16 | BX036048-08LD08S | 36" x 48" - CB FLAT TOP 8"W w/24"x30" HOLE F/F - 8" | 1
| WO17925 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | MH277 (439+85 RT) | BX048048-08TS48 | 48" x 48" - CB FT REDUCER 48" HOLE T/F - 8" | 1
| WO17916 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 262 (433+25 RT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 1
| WO17908 | Symon | 2026-08-20 | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 244 (428+40 RT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 1
| WO17653 | Symon | 2026-08-20 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 470 | BX024030-08LD08-15x27 | 24" x 30" - CB FLAT TOP 8"W w/15"x27" HOLE - 8" | 1
| WO17615 | Symon | 2026-08-20 | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 463 | BX2460-08BAVF | 24" x 60" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 1
| WO17245 | Symon | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 2 - BC 3.00x2.50 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 36" x 30" | 1
| WO17228 | Symon | 2026-08-20 | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 1 - BC 5.67x3.00 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 68" x 36" | 1
| WO17080 | Symon | 2026-08-20 | Contech Engineered Solutions | Sales Order #26-3104 | 10-KFPD0608 | CTS | 72" x 96" - BX FLAT LID 6inW w/SPECIAL F/F - 7.25" | 1
| WO16587 | Symon | 2026-08-20 | Endesol, Inc. | Sales Order #26-2945 | QL1 | Secondary Pour | SECONDARY POUR - Walls For Vault Sect. | 1
| WO15586 | Symon | 2026-08-20 | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | RAS/WAS VV | BX7272-08W08F06EB-VF | 72" x 72" - BX BASE w/FLANGE 08W/08F/06EF - 88" | 1
| WO15579 | Symon | 2026-08-20 | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | SCUM VV | BX6060-08W08F06EB-VF | 60" x 60" - BX BASE w/FLANGE 08W/08F/06EF - 84" | 1
| WO15475 | Boxes | 2026-08-20 | Bowling Green Winsupply | Sales Order #26-3001 | GT 2 | Secondary Pour | SECONDARY POUR - Baffle Wall | 1
| WO14835 | Symon | 2026-08-20 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P14-P15 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 2.00' HT x 6.42' LONG | 1
| WO14834 | Symon | 2026-08-20 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P13-P14 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1
| WO14833 | Symon | 2026-08-20 | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P13-P14 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1

## WorkOrderProductionScheduleRes
Internal ID | Document Number | Status | WO Form ID | Start Date | End Date | Form ID | Customer | SO# | Structure # | Item | Description | Concrete Weight | Quantity | Stack-It PART - DrawingImage | QR Label | Submittal Drawing link | Scheduling Method | Expected Ship Date
101.0 | WO18145 | Released | 36MH | 2026-08-20 | 2026-08-22 | 36MH | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-23 | MH036RSVF | 36" - MH RISER Custom Ht F/G - 62" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-23%2520P2%2520MH036RSVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-23%2520P2%2520MH036RSVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-23%2520Submittal.pdf
| WO18259 | Released | 48MH | 2026-08-20 | 2026-08-21 | 48MH |  |  |  | MH048RSVF |  |  | 1
| WO18258 | Released | 48MH | 2026-08-20 | 2026-08-21 | 48MH |  |  |  | MH048RSVF |  |  | 1
| WO18257 | Released | 48MH | 2026-08-20 | 2026-08-21 | 48MH |  |  |  | MH048RS72 |  |  | 1
| WO18252 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH |  |  |  | MH048LD12ECC |  |  | 1
| WO18251 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH |  |  |  | MH048BA48-B |  |  | 1
| WO18250 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH |  |  |  | MH048RS36 |  |  | 1
| WO18249 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH |  |  |  | MH048RS48 |  |  | 2
101.0 | WO18201 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Pace Contracting, LLC | Sales Order #25-4547P2 | MH-39-01A | MH048RS24 | 48" - MH RISER - 24" | 0.43015 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520P5%2520MH048RS24%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520P5%2520MH048RS24%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4547%2520-%2520WWTP%2520Improvements%2520-%2520Hydraulic%2520Expansion%2520-%2520202603004S/25-4547%2520MH-39-01A%2520Submittal.pdf
9.0 | WO18188 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH | Connhurst, LLC | Sales Order #26-1066 | A6 (10) | MH048LD12ECC | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 0.8 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A6%2520%252810%2529%2520P2%2520MH048LD12ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A6%2520%252810%2529%2520P2%2520MH048LD12ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%2520A6%2520%252810%2529%2520Submittal.pdf
| WO18131 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH |  |  |  | MH048CN36 |  |  | 2
10.0 | WO18062 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Luttrell & Sons, LLC | Sales Order #26-1814 | QL12 SS-MH | MH048BA42 | 48" - MH BASE - 42" | 1.1843 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL12%2520SS-MH%2520P1%2520MH048BA42%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL12%2520SS-MH%2520P1%2520MH048BA42%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL12%2520SS-MH%2520Submittal.pdf
9.0 | WO18059 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Luttrell & Sons, LLC | Sales Order #26-1814 | 0+68 SS-MH | MH048BA18 | 48" - MH BASE - 18" | 0.66432 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520P1%2520MH048BA18%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520P1%2520MH048BA18%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520Submittal.pdf
9.0 | WO18058 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Luttrell & Sons, LLC | Sales Order #26-1814 | 0+68 SS-MH | MH048RS72S | 48" - MH RISER SPECIAL - 72" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520P2%2520MH048RS72S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520P2%2520MH048RS72S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%25200%252B68%2520SS-MH%2520Submittal.pdf
| WO15601 | Released | 48MH | 2026-08-20 | 2026-08-21 | 48MH | Cumberland Pipeline LLC | Sales Order #25-4288P2 | A13 | MH048INVFX | 48" - MH INVERT CHANNEL w/XYPEX - FULL HEIGHT | 1.003 | 1
13.0 | WO13415 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Connhurst, LLC | Sales Order #26-1066 | 44+80 AR (14) | MH048LD12S | 48" - MH FLAT TOP w/30"x36" Hatch - 12" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252044%252B80%2520AR%2520%252814%2529%2520P4%2520MH048LD12S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252044%252B80%2520AR%2520%252814%2529%2520P4%2520MH048LD12S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252044%252B80%2520AR%2520%252814%2529%2520Submittal.pdf
12.0 | WO13410 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Connhurst, LLC | Sales Order #26-1066 | 20+49.85 AR (14) | MH048LD12S | 48" - MH FLAT TOP w/30"x36" Hatch - 12" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252020%252B49.85%2520AR%2520%252814%2529%2520P3%2520MH048LD12S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252020%252B49.85%2520AR%2520%252814%2529%2520P3%2520MH048LD12S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1066%2520-%2520Gunning%2520Pump%2520Station%2520-%2520Force%2520Main%2520-%2520202602004S/26-1066%252020%252B49.85%2520AR%2520%252814%2529%2520Submittal.pdf
110.0 | WO11841 | In Process | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Citco Water |  | 77+93 ARV | MH048CN36 | 48" - MH FLAT TOP w/ 24" ECC Hole - 12" | 0.8 | 2 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%252077%252B93%2520ARV%2520P3%2520MH048LD12ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%252077%252B93%2520ARV%2520P3%2520MH048LD12ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-4279%2520-%2520KYTC%2520Christian%2520Co%2520%2528251031%2529%2520-%2520202602004Q/25-4279%252077%252B93%2520ARV%2520Submittal.pdf
| WO11732 | In Process | 48MH | 2026-08-20 | 2026-08-24 | 48MH |  |  |  | MH048CN30 |  |  | 2
| WO11476 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH |  |  |  | MH048CN42X |  |  | 1
117.0 | WO10405 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Cumberland Pipeline LLC | Sales Order #26-1322B | 246-87 SS-MH | MH048BAVF | 48" - MH BASE (08"F) T/n - 38" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1322B%2520-%2520KYTC%2520Warren%2520Co%2520Call%2520104%2520%2528261503%2529%2520-%2520202602004M/26-1322B%2520246-87%2520SS-MH%2520P1%2520MH048BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1322B%2520-%2520KYTC%2520Warren%2520Co%2520Call%2520104%2520%2528261503%2529%2520-%2520202602004M/26-1322B%2520246-87%2520SS-MH%2520P1%2520MH048BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1322B%2520-%2520KYTC%2520Warren%2520Co%2520Call%2520104%2520%2528261503%2529%2520-%2520202602004M/26-1322B%2520246-87%2520SS-MH%2520Submittal.pdf
114.0 | WO10401 | Released | 48MH | 2026-08-20 | 2026-08-22 | 48MH | Cumberland Pipeline LLC | Sales Order #26-1322B | 179-84 SS-MH | MH048INVFG | 48" - MH INVERT CHANNEL - FULL HEIGHT | 1.003 | 1
| WO08015 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH |  |  |  | MH048BA36-KO |  |  | 1
1.0 | WO01970 | Released | 48MH | 2026-08-20 | 2026-08-24 | 48MH | Lawrence Construction & Leasing, Inc. | Sales Order #25-1385C | 51385C 2-2 | MH048RSVF | 48" - MH RISER Custom Ht T/G - 36" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1385C%2520W6%2520%2520Ph-II-A%2520Force%2520Main%2520Improvements%2520-%25202025110093/25-1385C%252051385C%25202-2%2520P1%2520MH048RSVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1385C%2520W6%2520%2520Ph-II-A%2520Force%2520Main%2520Improvements%2520-%25202025110093/25-1385C%252051385C%25202-2%2520P1%2520MH048RSVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1385C%2520W6%2520%2520Ph-II-A%2520Force%2520Main%2520Improvements%2520-%25202025110093/25-1385C%252051385C%25202-2%2520Submittal.pdf
101.0 | WO18205 | Released | 60MH | 2026-08-20 | 2026-08-22 | 60MH | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060RS72 | 60" - MH RISER T/G - 72" | 1.9297 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P2%2520MH060RS72%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P2%2520MH060RS72%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520Submittal.pdf
101.0 | WO18204 | Released | 60MH | 2026-08-20 | 2026-08-24 | 60MH | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060LD13-30ECC | 60" - MH FLAT TOP SPEC. (30" ECC HOLE) F/G - 13" | 0.75377 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P3%2520MH060LD13-30ECC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P3%2520MH060LD13-30ECC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520Submittal.pdf
101.0 | WO18202 | Released | 60MH | 2026-08-20 | 2026-08-24 | 60MH | Contech Engineered Solutions | Sales Order #26-3266 | 10-CS-5 | MH060BA18 | 60" - MH BASE T/n - 18" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P1%2520MH060BA18%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520P1%2520MH060BA18%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3266%2520903262%2520Enterprise%2520Leasing%2520Hazelwood%2520-%25202026080058/26-3266%252010-CS-5%2520Submittal.pdf
101.0 | WO18198 | Released | 60MH | 2026-08-20 | 2026-08-24 | 60MH | Hubert Excavating & Contracting | Sales Order #25-3579P6 | MH A11 Riser | MH060RSVFS | 60" - MH RISER Custom Ht- w/Coating T/G - 28" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3579%2520-%2520Lebanon%2520Rd%2520Clarks%2520Run%2520Trunk%2520Sewer%2520Ph%25202%2520-%25202026010121/25-3579%2520MH%2520A11%2520P3%2520MH060RSVFS%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3579%2520-%2520Lebanon%2520Rd%2520Clarks%2520Run%2520Trunk%2520Sewer%2520Ph%25202%2520-%25202026010121/25-3579%2520MH%2520A11%2520P3%2520MH060RSVFS%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3579%2520-%2520Lebanon%2520Rd%2520Clarks%2520Run%2520Trunk%2520Sewer%2520Ph%25202%2520-%25202026010121/25-3579%2520MH%2520A11%2520Submittal.pdf
102.0 | WO18169 | Released | 60MH | 2026-08-20 | 2026-08-24 | 60MH | ADS Advanced Drainage Systems, Inc. | Sales Order #26-3183 | STR-14 | MH060LD13CC | 60" - MH FLAT TOP w/24" Ctr. Hole F/G - 13" | 0.75377 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-14%2520P4%2520MH060LD13CC%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-14%2520P4%2520MH060LD13CC%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3183%2520ADS%2520Freedom-s%2520Way%2520Commons%2520-%25202026080048/26-3183%2520STR-14%2520Submittal.pdf
| WO18260 | Released | 72MH | 2026-08-20 | 2026-08-21 | 72MH |  |  |  | MH072TS15-48ECC |  |  | 1
102.0 | WO17416 | Released | 84MH | 2026-08-20 | 2026-08-25 | 84MH | Garney Companies, Inc. | Sales Order #26-1549P2 | MH-3-4 SS-MH | MH084BAEVFX | 84" - MH BASE w/FLANGE (12F/14EF) w/XYPEX - 93" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-3-4%2520SS-MH%2520P1%2520MH084BAEVFX%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-3-4%2520SS-MH%2520P1%2520MH084BAEVFX%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1549%2520Cowan%2520St-%2520Trunk%2520Sewer%2520-%2520202603011M/26-1549%2520MH-3-4%2520SS-MH%2520Submittal.pdf
4.0 | WO18073 | Released | 96MH | 2026-08-20 | 2026-08-22 | 96MH | Luttrell & Sons, LLC | Sales Order #26-1814 | QL6 | MH096RS84 | 96" - MH RISER - 84" | 3 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL6%2520P2%2520MH096RS84%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL6%2520P2%2520MH096RS84%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1814%2520-%2520Brownsville%2520Sewer%2520System%2520Additions%2520-%2520202606002Q/26-1814%2520QL6%2520Submittal.pdf
| WO18217 | Released | BLK | 2026-08-20 | 2026-08-22 | BLK |  |  |  | BLK242436AB |  |  | 1
| WO18212 | Released | Boxes | 2026-08-20 | 2026-08-22 | Boxes |  |  |  | BX2424-06B30-KO |  |  | 1
| WO18211 | Released | Boxes | 2026-08-20 | 2026-08-22 | Boxes |  |  |  | BX1818-06B24-KO |  |  | 1
135.0 | WO17921 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 272 (437+45 RT) | BX2436-08R36 | 24" x 36" - BOX RISER 8inW T/G - 36" | 0.65 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520P3%2520BX2436-08R36%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520P3%2520BX2436-08R36%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520Submittal.pdf
135.0 | WO17920 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 272 (437+45 RT) | BX2436-08R36 | 24" x 36" - BOX RISER 8inW F/G - 36" | 0.65 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520P4%2520BX2436-08R36%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520P4%2520BX2436-08R36%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520272%2520%2528437%252B45%2520RT%2529%2520Submittal.pdf
101.0 | WO17900 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Convergent Water Technologies, Inc. | Sales Order #26-3166 | FB2 ST-DBI | BX4848-08BAVF | 48" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3166%2520Rolling%2520Hills%2520PRETX%2520-%25202026070173/26-3166%2520FB2%2520ST-DBI%2520P1%2520BX4848-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3166%2520Rolling%2520Hills%2520PRETX%2520-%25202026070173/26-3166%2520FB2%2520ST-DBI%2520P1%2520BX4848-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3166%2520Rolling%2520Hills%2520PRETX%2520-%25202026070173/26-3166%2520FB2%2520ST-DBI%2520Submittal.pdf
11.0 | WO17808 | Released | Boxes | 2026-08-20 | 2026-08-21 | Boxes | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5088+83 RT CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205088%252B83%2520RT%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205088%252B83%2520RT%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205088%252B83%2520RT%2520CBBI-MOD%2520B1%2520Submittal.pdf
10.0 | WO17804 | Released | Boxes | 2026-08-20 | 2026-08-22 | Boxes | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5086+83 RT CBBI-MOD B1 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205086%252B83%2520RT%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205086%252B83%2520RT%2520CBBI-MOD%2520B1%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205086%252B83%2520RT%2520CBBI-MOD%2520B1%2520Submittal.pdf
130.0 | WO17746 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 262 (433+25 RT) | BX3648-08BA60 | 36" x 48" - BOX BASE 8inW- 8inF F/n - 60" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520P1%2520BX3648-08BA60%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520P1%2520BX3648-08BA60%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520Submittal.pdf
110.0 | WO17710 | Released | Boxes | 2026-08-20 | 2026-08-25 | Boxes | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 238 (426+83 LT) | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht F/n - 23" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520238%2520%2528426%252B83%2520LT%2529%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520238%2520%2528426%252B83%2520LT%2529%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520238%2520%2528426%252B83%2520LT%2529%2520Submittal.pdf
123.0 | WO17654 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 470 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 47" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520P1%2520BX24300808VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520P1%2520BX24300808VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520Submittal.pdf
135.0 | WO17617 | Released | Boxes | 2026-08-20 | 2026-08-24 | Boxes | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 589 | BX2436-08BVF | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 29" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520589%2520P1%2520BX2436-08BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520589%2520P1%2520BX2436-08BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520589%2520Submittal.pdf
128.0 | WO17609 | Released | Boxes | 2026-08-20 | 2026-08-22 | Boxes | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 476 | BX24300808VF | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 43" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520476%2520P1%2520BX24300808VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520476%2520P1%2520BX24300808VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520476%2520Submittal.pdf
1.0 | WO18167 | Released | FES | 2026-08-20 | 2026-08-24 | FES | Russell's Excavating | Sales Order #26-1227 | FES 24" TOE WALL | FES24B-TB | FLARED END SECTION BELL TOE BLOCK (OUTLET) | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520403-33%2520FES%2520TOE%2520P1%2520FES24B-TB%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520403-33%2520FES%2520TOE%2520P1%2520FES24B-TB%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1227%2520-%2520Project%2520Colt%2520%2520-%2520202604010Q/26-1227%2520403-33%2520FES%2520TOE%2520Submittal.pdf
101.0 | WO17903 | Released | FES | 2026-08-20 | 2026-08-21 | FES | Cleary Construction, Inc. | Sales Order #26-1077P7 | B5 | DRAINSLOPE | 24" x 36" - STORM INVERT CHANNEL (FLAT) - 4" THK | 1.003 | 1
| WO14643 | Released | FES | 2026-08-20 | 2026-08-22 | FES |  |  |  | FES12S |  |  | 1
| WO18255 | Released | HW | 2026-08-20 | 2026-08-22 | HW |  |  |  | HWBW24F |  |  | 1
| WO18254 | Released | HW | 2026-08-20 | 2026-08-22 | HW |  |  |  | HWSF15 |  |  | 1
| WO18253 | Released | HW | 2026-08-20 | 2026-08-22 | HW |  |  |  | HWSF18 |  |  | 1
| WO15156 | Released | HW | 2026-08-20 | 2026-08-22 | HW |  |  |  | HWPC42 |  |  | 1
| WO16552 | Released | JW | 2026-08-20 | 2026-08-22 | JW |  |  |  | MBI-TCCB-10-JJ |  |  | 30
| WO16422 | Released | JW | 2026-08-20 | 2026-08-22 | JW |  |  |  | MBI-TCCB-KYTC-9T-20FT-JJ |  |  | 4
32.0 | WO17839 | Released | Symon | 2026-08-20 | 2026-08-24 | KYTC MBI | Cleary Construction, Inc. | Sales Order #25-1684P14 | 4016+80 LT CBBI-MOD A1 (Top Phase) | CMBBIT9-A1SG | 24" x 120" - CB MED BAR BOX INLET 9A1 SAG - 17" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25204016%252B80%2520LT%2520CBBI-MOD%2520A1%2520P2%2520CMBBIT9-A1SG%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25204016%252B80%2520LT%2520CBBI-MOD%2520A1%2520P2%2520CMBBIT9-A1SG%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25204016%252B80%2520LT%2520CBBI-MOD%2520A1%2520Submittal.pdf
6.0 | WO17792 | Released | KYTC MBI | 2026-08-20 | 2026-08-21 | KYTC MBI | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5080+02 RT CBBI-MOD B1 (Top Phase) | CMBBIT9-B1RH | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205080%252B02%2520RT%2520CBBI-MOD%2520B1%2520P2%2520CMBBIT9-B1RH%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205080%252B02%2520RT%2520CBBI-MOD%2520B1%2520P2%2520CMBBIT9-B1RH%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205080%252B02%2520RT%2520CBBI-MOD%2520B1%2520Submittal.pdf
| WO18206 | Released | RCP | 2026-08-20 | 2026-08-22 | RCP |  |  |  | PIPRCP214 |  |  | 16
| WO18190 | Released | RCP | 2026-08-20 | 2026-08-22 | RCP |  |  |  | PIPRCP663 |  |  | 8
| WO18226 | Planned | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-FORIX-60-BC |  |  | 4
| WO18216 | Released | RET | 2026-08-20 | 2026-08-24 | RET |  |  |  | RET-SS-6-44-CG |  |  | 2
| WO18215 | Released | RET | 2026-08-20 | 2026-08-24 | RET |  |  |  | RET-SS-3SF-CG |  |  | 2
| WO16146 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-SS-MID-CAP |  |  | 1
| WO16145 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-SS-6-28-CG |  |  | 2
| WO16144 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-SS-24-44T-CG |  |  | 1
| WO16143 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-SS-24-86-CG |  |  | 4
| WO16142 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-SS-24-44-CG |  |  | 3
| WO16141 | Released | RET | 2026-08-20 | 2026-08-21 | RET |  |  |  | RET-FORIX-PARCP |  |  | 1
| WO16140 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-FORIX-PAR-BC |  |  | 2
| WO16139 | Released | RET | 2026-08-20 | 2026-08-20 | RET |  |  |  | RET-FORIX-PAR-BC |  |  | 1
| WO16136 | Released | RET | 2026-08-20 | 2026-08-21 | RET |  |  |  | RET-FORIX-30-BC |  |  | 33
101.0 | WO17082 | Released | Secondary Activity | 2026-08-20 | 2026-08-26 | Secondary Activity | Contech Engineered Solutions | Sales Order #26-3104 | 10-KFPD0608 | PSASSEMBLY | ASSEMBLY REQUIRED | 1.003 | 1 | https://icastinc.sharepoint.com/:b:/s/StackIT/IQD76Qjb7QNjTIV1ABYh8UFxARqt5S5ONefiz3yny-vlb6U?e=DoY0Rg
1.0 | WO16980 | Released | Secondary Activity | 2026-08-20 | 2026-08-26 | Secondary Activity | Endesol, Inc. | Sales Order #26-3067 | QL1 ACC1 | Special Pre-Assembly | Special Pre-Assembly Of Internal Materials Required | 1.003 | 1
3.0 | WO18137 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Josh King Excavation, LLC | Sales Order #25-2284D | L2 ST-TCI | BX2896-06BVF | 28" x 96" - BOX BASE 6inW- 6inF- Variable Ht F/n - 65" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284D%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026070188/25-2284D%2520L2%2520ST-TCI%2520P1%2520BX2896-06BVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284D%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026070188/25-2284D%2520L2%2520ST-TCI%2520P1%2520BX2896-06BVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2284D%2520Parks%2520at%2520Cane%2520Ridge%2520Ph-2B%2520-%25202026070188/25-2284D%2520L2%2520ST-TCI%2520Submittal.pdf
104.0 | WO17734 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 232 (424+73 RT) | BX024060-08LD08-1559 | 24" x 60" - BX FLAT LID 8inW- w/15"x59" HOLE (KYTC DBI-13S) F/F - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520232%2520%2528424%252B73%2520RT%2529%2520P2%2520BX024060-08LD08-1559%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520232%2520%2528424%252B73%2520RT%2529%2520P2%2520BX024060-08LD08-1559%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520232%2520%2528424%252B73%2520RT%2529%2520Submittal.pdf
2.0 | WO18218 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Louisville Paving and Construction | Sales Order #25-2952 | MSD HW | HWMSD12 | End Treatment 12" MSD Std. Straight Headwall | 1 | 1
12.0 | WO18121 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Cleary Construction, Inc. | Sales Order #25-1684P14 | 5090+98 RT CBBI-MOD B1 | BX036036-08TS024036 | 36" x 36" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 0.5 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205090%252B98%2520RT%2520CBBI-MOD%2520B1%2520P2%2520BX036036-08TS024036%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205090%252B98%2520RT%2520CBBI-MOD%2520B1%2520P2%2520BX036036-08TS024036%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-1684P14%2520KYTC%2520Jefferson%2520Co-%2520Call%2520200%2520%2528251007%2529%2520-%25202026070103/25-1684P14%25205090%252B98%2520RT%2520CBBI-MOD%2520B1%2520Submittal.pdf
101.0 | WO18108 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Convergent Water Technologies, Inc. | Sales Order #26-1706 | QL1 | Secondary Pour | SECONDARY POUR - WEIR WALL | 1.003 | 1
4.0 | WO18075 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Luttrell & Sons, LLC | Sales Order #26-1814 | QL6 | Secondary Pour | SECONDARY POUR - EXT. FLANGE | 1.003 | 1
3.0 | WO18035 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Clarksville Gas & Water Dept. | Sales Order #26-1735 | QL2 | BX120120-08LD08SP | 120" x 120" - BX FLAT LID 8inW w/2x 42"x72" HATCHES - 8" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1735%2520-%2520City%2520Of%2520Clarksville%2520Vaults%2520-%2520202606006T/26-1735%2520QL2%2520P3%2520BX120120-08LD08SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1735%2520-%2520City%2520Of%2520Clarksville%2520Vaults%2520-%2520202606006T/26-1735%2520QL2%2520P3%2520BX120120-08LD08SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1735%2520-%2520City%2520Of%2520Clarksville%2520Vaults%2520-%2520202606006T/26-1735%2520QL2%2520Submittal.pdf
107.0 | WO17959 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-19 | BX2436-06LD08-SP | 24" x 36" - BX FLAT LID 8inW w/24"x30" HOLE F/F - 6" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-19%2520P2%2520BX2436-06LD08-SP%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-19%2520P2%2520BX2436-06LD08-SP%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-19%2520Submittal.pdf
104.0 | WO17948 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #26-1000P2 | DBI-16 | BX036048-08LD08S | 36" x 48" - CB FLAT TOP 8"W w/24"x30" HOLE F/F - 8" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-16%2520P3%2520BX036048-08LD08S%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-16%2520P3%2520BX036048-08LD08S%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1000P2%2520Clark%2520Distributing%2520New%2520HQ%2520-%2520Site%2520Structures%2520-%25202026070078/26-1000P2%2520DBI-16%2520Submittal.pdf
138.0 | WO17925 | Released | Symon | 2026-08-20 | 2026-08-26 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | MH277 (439+85 RT) | BX048048-08TS48 | 48" x 48" - CB FT REDUCER 48" HOLE T/F - 8" | 1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520MH277%2520%2528439%252B85%2520RT%2529%2520P2%2520BX048048-08TS48%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520MH277%2520%2528439%252B85%2520RT%2529%2520P2%2520BX048048-08TS48%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520MH277%2520%2528439%252B85%2520RT%2529%2520Submittal.pdf
130.0 | WO17916 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 262 (433+25 RT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 0.5 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520P2%2520BX036048-08TS024036%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520P2%2520BX036048-08TS024036%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520262%2520%2528433%252B25%2520RT%2529%2520Submittal.pdf
115.0 | WO17908 | Released | Symon | 2026-08-20 | 2026-08-25 | Symon | Scotty's Contracting & Stone, LLC | Sales Order #24-4208P2 | 244 (428+40 RT) | BX036048-08TS024036 | 36" x 48" - CB FT REDUCER 24"X36" HOLE T/F - 8" | 0.5 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520244%2520%2528428%252B40%2520RT%2529%2520P2%2520BX036048-08TS024036%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520244%2520%2528428%252B40%2520RT%2529%2520P2%2520BX036048-08TS024036%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/24-4208%2520-%2520KYTC%2520Christian%2520Co-%2520Call%2520100%2520%2528ID%2520241018%2529%2520-%25202025090121/24-4208%2520244%2520%2528428%252B40%2520RT%2529%2520Submittal.pdf
123.0 | WO17653 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 470 | BX024030-08LD08-15x27 | 24" x 30" - CB FLAT TOP 8"W w/15"x27" HOLE - 8" | 0.4 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520P2%2520BX024030-08LD08-15X27%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520P2%2520BX024030-08LD08-15X27%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520470%2520Submittal.pdf
131.0 | WO17615 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Eaton Asphalt Paving Co., Inc. | Sales Order #25-3193P4 | 463 | BX2460-08BAVF | 24" x 60" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520463%2520P1%2520BX2460-08BAVF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520463%2520P1%2520BX2460-08BAVF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3193%2520-%2520KYTC%2520Kenton%2520Co%2520Call%2520328%2520%2528251320%2529%2520%2520%2520-%25202026010023/25-3193%2520463%2520Submittal.pdf
102.0 | WO17245 | Released | Symon | 2026-08-20 | 2026-08-21 | Symon | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 2 - BC 3.00x2.50 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 36" x 30" | 0.1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2504%2520UK%2520BP9%2520Site%2520Thermal%2520and%2520Electric%2520Utilities%2520-%25202025120161/25-2504%2520BC%2520RUN%25202%2520-%2520BC%25203.00x2.50%2520P6%2520CBC%2520Shop.pdf
103.0 | WO17228 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Cleary Construction, Inc. | Sales Order #25-2504 | BC RUN 1 - BC 5.67x3.00 | CBC | BOX CULV. (3-sided) 08W08T - 5.75' - 68" x 36" | 0.1 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-2504%2520UK%2520BP9%2520Site%2520Thermal%2520and%2520Electric%2520Utilities%2520-%25202025120161/25-2504%2520BC%2520RUN%25201%2520-%2520BC%25205.67x3.00%2520P5%2520CBC%2520Shop.pdf
101.0 | WO17080 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | Contech Engineered Solutions | Sales Order #26-3104 | 10-KFPD0608 | CTS | 72" x 96" - BX FLAT LID 6inW w/SPECIAL F/F - 7.25" | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3104%2520833109%2520WaWa%2520No-%25207018%2520-%25202026070238/26-3104%252010-KFPD0608%2520P2%2520CTS%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3104%2520833109%2520WaWa%2520No-%25207018%2520-%25202026070238/26-3104%252010-KFPD0608%2520P2%2520CTS%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3104%2520833109%2520WaWa%2520No-%25207018%2520-%25202026070238/26-3104%252010-KFPD0608%2520Submittal.pdf
1.0 | WO16587 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Endesol, Inc. | Sales Order #26-2945 | QL1 | Secondary Pour | SECONDARY POUR - Walls For Vault Sect. | 1.003 | 1
2.0 | WO15586 | Released | Symon | 2026-08-20 | 2026-08-24 | Symon | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | RAS/WAS VV | BX7272-08W08F06EB-VF | 72" x 72" - BX BASE w/FLANGE 08W/08F/06EF - 88" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520RAS_WAS%2520VV%2520P1%2520BX7272-08W08F06EB-VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520RAS_WAS%2520VV%2520P1%2520BX7272-08W08F06EB-VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520RAS_WAS%2520VV%2520Submittal.pdf
2.0 | WO15579 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | W Principles, LLC c/o Carter Caves State Resort Park | Sales Order #25-3187P3 | SCUM VV | BX6060-08W08F06EB-VF | 60" x 60" - BX BASE w/FLANGE 08W/08F/06EF - 84" | 0.25075 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520VV%2520P1%2520BX6060-08W08F06EB-VF%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520VV%2520P1%2520BX6060-08W08F06EB-VF%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/25-3187%2520-%2520Carter%2520Caves%2520WTP%2520Upgrades%2520Ph%25203%2520-%25202025120031/25-3187%2520SCUM%2520VV%2520Submittal.pdf
2.0 | WO15475 | Released | Boxes | 2026-08-20 | 2026-08-22 | Symon | Bowling Green Winsupply | Sales Order #26-3001 | GT 2 | Secondary Pour | SECONDARY POUR - Baffle Wall | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-3001%2520-%2520Gunnison%2520Way%2520Grease%2520Traps%2520-%25202026070024/26-3001%2520GT%25202%2520P1%2520BX60120-06W06F-BA54%2520Shop.pdf
14.0 | WO14835 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P14-P15 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 2.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P14-P15%2520P3%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P14-P15%2520P3%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P14-P15%2520Submittal.pdf
13.0 | WO14834 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P13-P14 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520P1%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520P1%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520Submittal.pdf
13.0 | WO14833 | Released | Symon | 2026-08-20 | 2026-08-22 | Symon | Hall Contracting of Kentucky, Inc | Sales Order #26-1333 | WALL P13-P14 | Custom Wall | 77" x 6" - WALL PANEL 6" THICK F/F - 3.00' HT x 6.42' LONG | 1.003 | 1 | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520P2%2520CUSTOM%2520WALL%2520Shop.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520P2%2520CUSTOM%2520WALL%2520CarrierQR.pdf | https://docs.google.com/viewer?url=http://fileshare.icastinc.com/shared/26-1333%2520-%2520Mitchell%2520Hill%2520Road%2520Project%2520-%25202026040041/26-1333%2520WALL%2520P13-P14%2520Submittal.pdf