## Delivery Plan
Priority | Structure | Type | Size | Total Wt | Balance to Ship | Earliest Ship Date | Production End | Base Prod End | Top Phase Prod End | Status | Next Out | Load #
1 | 15+86 MOD MH TYPE C | KYTC Manhole Type C (MOD) | 84x132 | 50489 | 3200 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | PARTIAL |  | LD00005585
2 | 16+15 JB-B1 INLET 36 | KYTC JB-B1 Inlet 36 | 60x60 | 16651 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 |  | SHIPPED |  | LD00005582
3 | 5090+98 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 48x48 | 16389 | 16389 | 2026-09-02 | 2026-08-29 | 2026-08-29 | 2026-08-25
4 | 5092+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 13451 | 13451 | 2026-09-02 | 2026-08-27 | 2026-08-27 | 2026-08-26
5 | 5094+66 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 12243 | 12243 | 2026-09-02 | 2026-08-31 | 2026-08-31 | 2026-08-27
6 | 5095+00 LT JB-A | Junction Box | 36x48 | 8165 | 8165 | 2026-09-02 | 2026-08-27 | 2026-08-27
7 | 5096+43 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 11744 | 11744 | 2026-09-08 | 2026-08-31 | 2026-08-31 | 2026-08-28
8 | 5097+50 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 11919 | 11919 | 2026-09-08 | 2026-08-31 | 2026-08-28 | 2026-08-31
9 | 5098+23 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 9171 | 9171 | 2026-09-08 | 2026-08-31 | 2026-08-29 | 2026-08-31
10 | 5100+05 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8763 | 8763 | 2026-09-08 | 2026-09-01 | 2026-08-28 | 2026-09-01
11 | 5101+20 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8287 | 8287 | 2026-09-08 | 2026-09-02 | 2026-09-01 | 2026-09-02
12 | 4016+80 LT CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 7878 | 2026-09-08 | 2026-09-01 | 2026-09-01 | 2026-08-21
13 | 4016+28 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 7878 | 2026-09-08 | 2026-09-03 | 2026-09-01 | 2026-09-03
14 | 4014+56 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7776 | 7776 | 2026-09-14 | 2026-09-04 | 2026-09-04 | 2026-09-04
15 | 4013+85 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7368 | 7368 | 2026-09-14 | 2026-09-08 | 2026-09-08 | 2026-09-08
16 | 4012+55 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x40 | 7878 | 7878 | 2026-09-14 | 2026-09-09 | 2026-09-08 | 2026-09-09
17 | 4010+98 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x36 | 10616 | 10616 | 2026-09-14 | 2026-09-10 | 2026-09-08 | 2026-09-10
18 | 4010+54 LT CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | 24x36 | 7845 | 7845 | 2026-09-14 | 2026-09-18 | 2026-09-11 | 2026-09-18
19 | 4010+04 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7896 | 7896 | 2026-09-14 | 2026-09-12 | 2026-09-12 | 2026-09-11
20 | 5088+48 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8100 | 8100 | 2026-09-02 | 2026-09-14 | 2026-08-27 | 2026-09-14
21 | 5086+13 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8865 | 8865 | 2026-09-02 | 2026-09-14 | 2026-08-27 | 2026-09-14
22 | 5083+65 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 11569 | 11569 | 2026-09-02 | 2026-09-15 | 2026-08-29 | 2026-09-15
23 | 5081+13 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 12981 | 12981 | 2026-09-02 | 2026-09-16 | 2026-09-01 | 2026-09-16
24 | 5078+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 9976 | 9976 | 2026-09-02 | 2026-09-17 | 2026-08-25 | 2026-09-17
25 | 5077+33 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8445 | 8445 | 2026-08-27 | 2026-09-18 | 2026-08-25 | 2026-09-18 |  | SHIPPING 8/27
26 | 5094+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 4000 | 2026-08-27 | 2026-09-21 | 2026-08-24 | 2026-09-21 | PARTIAL | SHIPPING 8/27 | LD00005594
27 | 5092+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 4000 | 2026-08-27 | 2026-09-21 | 2026-08-24 | 2026-09-21 | PARTIAL | SHIPPING 8/27 | LD00005594
28 | 5090+98 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x36 | 10281 | 4000 | 2026-08-27 | 2026-09-22 | 2026-08-21 | 2026-09-22 | PARTIAL | SHIPPING 8/27 | LD00005582
29 | 5088+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 0 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | SHIPPED |  | LD00005582
30 | 5086+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 4000 | 2026-08-21 | 2026-09-24 | 2026-08-21 | 2026-09-24 | PARTIAL |  | LD00005582
31 | 5084+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 4000 | 2026-08-21 | 2026-09-25 | 2026-08-21 | 2026-09-25 | PARTIAL |  | LD00005594
32 | 5082+33 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8389 | 4000 | 2026-08-21 | 2026-09-28 | 2026-08-19 | 2026-09-28 | PARTIAL |  | LD00005520
33 | 5081+13 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 10453 | 0 | 2026-08-21 | 2026-08-24 | 2026-08-19 | 2026-08-24 | SHIPPED |  | LD00005520, LD00005594
34 | 5080+02 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 7878 | 0 | 2026-08-17 | 2026-08-21 | 2026-08-19 | 2026-08-21 | SHIPPED |  | LD00005520
35 | 5077+33 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 10531 | 0 | 2026-08-17 | 2026-08-19 | 2026-08-18 | 2026-08-19 | SHIPPED |  | LD00005387
36 | 5074+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8241 | 4241 | 2026-08-27 | 2026-08-28 | 2026-08-28 | 2026-08-15 | PARTIAL | SHIPPING 8/27 | LD00005594
37 | 5074+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8287 | 0 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 2026-08-18 | SHIPPED |  | LD00005387
38 | 11+79 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8955 | 4000 | 2026-08-27 | 2026-09-28 | 2026-08-24 | 2026-09-28 | PARTIAL | SHIPPING 8/27 | LD00005594
38 | 14+27 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 11570 | 11570 | 2026-08-27 | 2026-09-29 | 2026-08-26 | 2026-09-29 |  | SHIPPING 8/27
39 | 15+26 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 16773 | 4000 | 2026-08-27 | 2026-10-01 | 2026-08-24 | 2026-10-01 | PARTIAL | SHIPPING 8/27 | LD00005594
40 | 15+26 DBI 2-MOD | KYTC Drop Box Inlet Type 2 | 36x48 | 7522 | 0 | 2026-08-27 | 2026-08-21 | 2026-08-21 |  | SHIPPED |  | LD00005582
41 | 16+47 DBI 2-MOD | KYTC Drop Box Inlet Type 2 | 36x48 | 6934 | 0 | 2026-08-21 | 2026-08-17 | 2026-08-17 |  | SHIPPED |  | LD00005594
44 | 17+62 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 36x48 | 12576 | 4000 | 2026-08-21 | 2026-08-25 | 2026-08-17 | 2026-08-25 | PARTIAL |  | LD00005520
45 | 18+23 CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | 24x36 | 8967 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-17 | 2026-08-21 | SHIPPED |  | LD00005520
46 | 18+72 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8763 | 4000 | 2026-08-17 | 2026-10-03 | 2026-08-19 | 2026-10-03 | PARTIAL |  | LD00005520
47 | 19+71 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8712 | 0 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 2026-08-14 | SHIPPED |  | LD00005387, LD00005594
48 | 22+18 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 24x36 | 8100 | 4000 | 2026-08-17 | 2026-08-21 | 2026-08-21 | 2026-08-17 | PARTIAL |  | LD00005520
49 | 5102+27 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 24x36 | 5288 | 5288 | 2026-09-08 | 2026-09-16 | 2026-09-16
50 | 5102+98 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 24x30 | 5305 | 5305 | 2026-09-08 | 2026-09-10 | 2026-09-10
51 | 5103+84 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 24x30 | 5305 | 5305 | 2026-09-14 | 2026-09-14 | 2026-09-14
52 | 5014+69 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 (MOD) | 24x30 | 5033 | 5033 | 2026-09-14 | 2026-09-14 | 2026-09-14
53 | 5107+56 DBI TYPE 1-NA | KYTC CMBBI Pipe Chamber | 36x48 | 8077 | 8077 | 2026-09-14 | 2026-09-11 | 2026-09-11
54 | 4006+00 MH-A | KYTC Manhole Type A | 48 Dia. | 5147 | 5147 | 2026-09-18 | 2026-09-04 | 2026-09-04
55 | 5116+07 RT DBI TYPE 1-MOD | KYTC Drop Box Inlet Type 1 | 36x36 | 6050 | 6050 | 2026-09-18 | 2026-09-11 | 2026-09-11
56 | 5116+07 LT DBI TYPE 1-MOD | KYTC Drop Box Inlet Type 1 | 36x36 | 4580 | 4580 | 2026-09-18 | 2026-09-11 | 2026-09-11
57 | 4003+50 LT CBIB INLET 21 | KYTC CBI Ty B Pipe Chamber | 24x24 | 7958 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-17 |  | SHIPPED |  | LD00005387
58 | 4001+70 LT CBIB INLET 19 | KYTC CBI Ty B Pipe Chamber | 24x36 | 8843 | 0 | 2026-08-17 | 2026-08-19 | 2026-08-19 |  | SHIPPED |  | LD00005387
59 | 4001+57 RT DBI 5A INLET 17 | KYTC Drop Box Inlet Type 5A | 36x48 | 5257 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-17 |  | SHIPPED |  | LD00005387
201 | HWSF15 | 15in Sloped & Flared Headwall |  | 37932 | 18966 | 2026-08-21 |  |  |  | PARTIAL |  | LD00005520, LD00005522
202 | HWPC36 | 36in Pipe Culvert Headwall |  | 34080 | 17040 | 2026-08-21 |  |  |  | PARTIAL |  | LD00005522
| TOTAL |  |  | 633520 | 369005

## Load Plan
SHIPPED - delivered loads (NetSuite Load #)
LD00005387 ¦ Shipped 2026-08-21 ¦ Driver Mason (IPL) ¦ 45,588 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005387 | 5077+33 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-19 | 2026-08-21
LD00005387 | 5074+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-18 | 2026-08-21
LD00005387 | 19+71 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-18 | 2026-08-21
LD00005387 | 4003+50 LT CBIB INLET 21 | KYTC CBI Ty B Pipe Chamber | SHIPPED | 2026-08-17 | 2026-08-21
LD00005387 | 4001+70 LT CBIB INLET 19 | KYTC CBI Ty B Pipe Chamber | SHIPPED | 2026-08-19 | 2026-08-21
LD00005387 | 4001+57 RT DBI 5A INLET 17 | KYTC Drop Box Inlet Type 5A | SHIPPED | 2026-08-17 | 2026-08-21
|  | LOAD WEIGHT (NetSuite) | 45588
LD00005520 ¦ Shipped 2026-08-21 ¦ Driver Jon Tingle (IPL) ¦ 48,287 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005520 | 5082+33 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-28 | 2026-08-21
LD00005520 | 5081+13 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-24 | 2026-08-21
LD00005520 | 5080+02 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-21 | 2026-08-21
LD00005520 | 17+62 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-08-25 | 2026-08-21
LD00005520 | 18+23 CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-21 | 2026-08-21
LD00005520 | 18+72 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-10-03 | 2026-08-21
LD00005520 | 22+18 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-08-21 | 2026-08-21
LD00005520 | HWSF15 | 15in Sloped & Flared Headwall | PARTIAL |  | 2026-08-21
|  | LOAD WEIGHT (NetSuite) | 48287
LD00005522 ¦ Shipped 2026-08-21 ¦ Driver James Eaves (IPL) ¦ 32,846 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005522 | HWSF15 | 15in Sloped & Flared Headwall | PARTIAL |  | 2026-08-21
LD00005522 | HWPC36 | 36in Pipe Culvert Headwall | PARTIAL |  | 2026-08-21
|  | LOAD WEIGHT (NetSuite) | 32846
LD00005582 ¦ Shipped 2026-08-26 ¦ Driver Bill T. Truck #1 ¦ 42,211 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005582 | 16+15 JB-B1 INLET 36 | KYTC JB-B1 Inlet 36 | SHIPPED | 2026-08-21 | 2026-08-26
LD00005582 | 5090+98 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-22 | 2026-08-26
LD00005582 | 5088+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-26 | 2026-08-26
LD00005582 | 5086+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-24 | 2026-08-26
LD00005582 | 15+26 DBI 2-MOD | KYTC Drop Box Inlet Type 2 | SHIPPED | 2026-08-21 | 2026-08-26
|  | LOAD WEIGHT (NetSuite) | 42211
LD00005585 ¦ Shipped 2026-08-26 ¦ Driver Bill T. Truck #2 ¦ 47,290 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005585 | 15+86 MOD MH TYPE C | KYTC Manhole Type C (MOD) | PARTIAL | 2026-08-21 | 2026-08-26
|  | LOAD WEIGHT (NetSuite) | 47290
LD00005594 ¦ Shipped 2026-08-26 ¦ Driver Jon Tingle (IPL) ¦ 48,297 lb ¦ Confirmed
Load # | Structure | Type | Status | Production End | Ship Date
LD00005594 | 5094+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-21 | 2026-08-26
LD00005594 | 5092+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-21 | 2026-08-26
LD00005594 | 5084+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-25 | 2026-08-26
LD00005594 | 5081+13 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-24 | 2026-08-26
LD00005594 | 5074+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-08-28 | 2026-08-26
LD00005594 | 11+79 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-09-28 | 2026-08-26
LD00005594 | 15+26 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | PARTIAL | 2026-10-01 | 2026-08-26
LD00005594 | 16+47 DBI 2-MOD | KYTC Drop Box Inlet Type 2 | SHIPPED | 2026-08-17 | 2026-08-26
LD00005594 | 19+71 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | SHIPPED | 2026-08-18 | 2026-08-26
|  | LOAD WEIGHT (NetSuite) | 48297
|  | TOTAL SHIPPED (6 loads) | 264519
STILL TO SHIP - planned loads (48,000 lb target, strict priority order)
Planned Load 1 ¦ Earliest Ship Date 2026-08-17
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
46 | 18+72 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-17 | 2026-10-03
48 | 22+18 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-17 | 2026-08-21
|  | LOAD TOTAL | 8000
Planned Load 2 ¦ Earliest Ship Date 2026-08-21
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
1 | 15+86 MOD MH TYPE C | KYTC Manhole Type C (MOD) | 3200 | 2026-08-21 | 2026-08-21
30 | 5086+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-21 | 2026-09-24
31 | 5084+83 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-21 | 2026-09-25
32 | 5082+33 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-21 | 2026-09-28
44 | 17+62 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-21 | 2026-08-25
201 | HWSF15 | 15in Sloped & Flared Headwall | 18966 | 2026-08-21
|  | LOAD TOTAL | 38166
Planned Load 3 ¦ Earliest Ship Date 2026-08-21
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
202 | HWPC36 | 36in Pipe Culvert Headwall | 17040 | 2026-08-21
|  | LOAD TOTAL | 17040
Planned Load 4 ¦ Earliest Ship Date 2026-08-27 ¦ NEXT OUT - 8/27
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
25 | 5077+33 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 8445 | 2026-08-27 | 2026-09-18
26 | 5094+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-27 | 2026-09-21
27 | 5092+97 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-27 | 2026-09-21
28 | 5090+98 RT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-27 | 2026-09-22
36 | 5074+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4241 | 2026-08-27 | 2026-08-28
38 | 11+79 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-27 | 2026-09-28
38 | 14+27 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 11570 | 2026-08-27 | 2026-09-29
39 | 15+26 CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 4000 | 2026-08-27 | 2026-10-01
|  | LOAD TOTAL | 44256
Planned Load 5 ¦ Earliest Ship Date 2026-09-02
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
3 | 5090+98 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 16389 | 2026-09-02 | 2026-08-29
4 | 5092+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 13451 | 2026-09-02 | 2026-08-27
5 | 5094+66 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 12243 | 2026-09-02 | 2026-08-31
|  | LOAD TOTAL | 42083
Planned Load 6 ¦ Earliest Ship Date 2026-09-02
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
6 | 5095+00 LT JB-A | Junction Box | 8165 | 2026-09-02 | 2026-08-27
20 | 5088+48 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 8100 | 2026-09-02 | 2026-09-14
21 | 5086+13 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 8865 | 2026-09-02 | 2026-09-14
22 | 5083+65 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 11569 | 2026-09-02 | 2026-09-15
|  | LOAD TOTAL | 36699
Planned Load 7 ¦ Earliest Ship Date 2026-09-02
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
23 | 5081+13 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 12981 | 2026-09-02 | 2026-09-16
24 | 5078+83 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 9976 | 2026-09-02 | 2026-09-17
|  | LOAD TOTAL | 22957
Planned Load 8 ¦ Earliest Ship Date 2026-09-08
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
7 | 5096+43 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 11744 | 2026-09-08 | 2026-08-31
8 | 5097+50 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 11919 | 2026-09-08 | 2026-08-31
9 | 5098+23 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 9171 | 2026-09-08 | 2026-08-31
10 | 5100+05 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 8763 | 2026-09-08 | 2026-09-01
|  | LOAD TOTAL | 41597
Planned Load 9 ¦ Earliest Ship Date 2026-09-08
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
11 | 5101+20 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 8287 | 2026-09-08 | 2026-09-02
12 | 4016+80 LT CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | 7878 | 2026-09-08 | 2026-09-01
13 | 4016+28 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 7878 | 2026-09-08 | 2026-09-03
49 | 5102+27 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 5288 | 2026-09-08 | 2026-09-16
50 | 5102+98 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 5305 | 2026-09-08 | 2026-09-10
|  | LOAD TOTAL | 34636
Planned Load 10 ¦ Earliest Ship Date 2026-09-14
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
14 | 4014+56 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 7776 | 2026-09-14 | 2026-09-04
15 | 4013+85 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 7368 | 2026-09-14 | 2026-09-08
16 | 4012+55 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 7878 | 2026-09-14 | 2026-09-09
17 | 4010+98 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 10616 | 2026-09-14 | 2026-09-10
18 | 4010+54 LT CBBI-MOD A1 | KYTC CMBBI Pipe Chamber | 7845 | 2026-09-14 | 2026-09-18
|  | LOAD TOTAL | 41483
Planned Load 11 ¦ Earliest Ship Date 2026-09-14
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
19 | 4010+04 LT CBBI-MOD B1 | KYTC CMBBI Pipe Chamber | 7896 | 2026-09-14 | 2026-09-12
51 | 5103+84 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 | 5305 | 2026-09-14 | 2026-09-14
52 | 5014+69 LT DBI-10 MOD | KYTC Drop Box Inlet Type 10 (MOD) | 5033 | 2026-09-14 | 2026-09-14
53 | 5107+56 DBI TYPE 1-NA | KYTC CMBBI Pipe Chamber | 8077 | 2026-09-14 | 2026-09-11
|  | LOAD TOTAL | 26311
Planned Load 12 ¦ Earliest Ship Date 2026-09-18
Priority | Structure | Type | Balance Wt | Earliest Ship Date | Production End
54 | 4006+00 MH-A | KYTC Manhole Type A | 5147 | 2026-09-18 | 2026-09-04
55 | 5116+07 RT DBI TYPE 1-MOD | KYTC Drop Box Inlet Type 1 | 6050 | 2026-09-18 | 2026-09-11
56 | 5116+07 LT DBI TYPE 1-MOD | KYTC Drop Box Inlet Type 1 | 4580 | 2026-09-18 | 2026-09-11
|  | LOAD TOTAL | 15777
|  | GRAND TOTAL TO SHIP | 369005
|  | PLANNED LOADS | 12

## Production Schedule
Priority | Structure | Phase | Description | Size | Weight | WO # | Sched Start | Sched End | Actual Start | Actual End | Status
1 | 4001+57 RT DBI 5A INLET 17 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 25" | 36 x 48 | 5257 | WO17851 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Built
2 | 4001+70 LT CBIB INLET 19 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3523 | WO17850 | 2026-08-18 | 2026-08-20 | 2026-08-19 | 2026-08-19 | Built
2 | 4001+70 LT CBIB INLET 19 | Base | 24" x 36" - CB FT REDUCER 24"X24" HOLE - 8" | 24 x 36 | 1010 | WO17926 | 2026-08-14 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
3 | 4003+50 LT CBIB INLET 21 | Base | 24" x 24" - BOX BASE 8inW- 8inF - 36" | 24 x 24 | 3648 | WO17849 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Built
5 | 5077+33 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 52" | 24 x 36 | 6531 | WO17791 | 2026-08-17 | 2026-08-20 | 2026-08-18 | 2026-08-18 | Built
5 | 5077+33 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17790 | 2026-08-18 | 2026-08-20 | 2026-08-19 | 2026-08-19 | Built
6 | 5080+02 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17793 | 2026-08-18 | 2026-08-21 | 2026-08-19 | 2026-08-19 | Built
6 | 5080+02 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17792 | 2026-08-20 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
7 | 5081+13 RT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 36 x 48 | 5476 | WO17789 | 2026-08-18 | 2026-08-21 | 2026-08-19 | 2026-08-19 | Built
7 | 5081+13 RT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 977 | WO18134 | 2026-08-18 | 2026-08-20 | 2026-08-19 | 2026-08-19 | Built
7 | 5081+13 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 36 x 48 | 4000 | WO17788 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
8 | 5082+33 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 31" | 24 x 36 | 4389 | WO17795 | 2026-08-18 | 2026-08-20 | 2026-08-19 | 2026-08-19 | Built
8 | 5082+33 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17794 | 2026-09-25 | 2026-09-28 |  |  | Released
9 | 5084+83 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17800 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
9 | 5084+83 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17799 | 2026-09-24 | 2026-09-25 |  |  | Released
10 | 16+15 JB-B1 INLET 36 | Base | 60" x 60" - BX FLAT LID 8inW SPEC. (KY JB-B1) - 8" | 60 x 60 | 3574 | WO17858 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
10 | 16+15 JB-B1 INLET 36 | Base | 60" x 60" - BOX BASE 8inW- 8inF - 66" | 60 x 60 | 13077 | WO17859 | 2026-08-15 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
10 | 16+15 JB-B1 INLET 36 | Base | SECONDARY POUR - WALLS | 60 x 60 | 0 | WO17860 | 2026-08-17 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Built
10 | 5086+83 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17804 | 2026-08-20 | 2026-08-22 | 2026-08-21 | 2026-08-21 | Built
10 | 5086+83 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17803 | 2026-09-23 | 2026-09-24 |  |  | Released
11 | 15+86 MOD MH TYPE C | Base | 84" x 132" - CB FT REDUCER 48" HOLE - 10" | 84 x 132 | 10901 | WO17861 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
11 | 15+86 MOD MH TYPE C | Base | 84" x 132" - BX BASE w/FLANGE 08W/12F/08EF - 84" | 84 x 132 | 36186 | WO17862 | 2026-08-18 | 2026-08-21 | 2026-08-19 | 2026-08-19 | Built
11 | 5088+83 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17808 | 2026-08-20 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
11 | 5088+83 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17807 | 2026-09-22 | 2026-09-23 | 2026-08-26 | 2026-08-26 | Built
12 | 5090+98 RT CBBI-MOD B1 | Base | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 36" | 36 x 36 | 5046 | WO17813 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
12 | 5090+98 RT CBBI-MOD B1 | Base | 36" x 36" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 36 | 1235 | WO18121 | 2026-08-20 | 2026-08-22 | 2026-08-21 | 2026-08-21 | Built
12 | 5090+98 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 36 x 36 | 4000 | WO17812 | 2026-09-21 | 2026-09-22 |  |  | Released
13 | 5092+97 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17821 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
13 | 5092+97 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17820 | 2026-09-19 | 2026-09-21 |  |  | Released
14 | 5094+97 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17823 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
14 | 5094+97 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17822 | 2026-09-18 | 2026-09-21 |  |  | Released
20 | 5083+65 LT CBBI-MOD B1 | Base | 24" x 36" - BOX RISER 8inW- Variable Ht - 33" | 24 x 36 | 3367 | WO17797 | 2026-08-26 | 2026-08-29 |  |  | Released
20 | 5083+65 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF - 30" | 24 x 36 | 4202 | WO17798 | 2026-08-25 | 2026-08-27 |  |  | Released
20 | 5083+65 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17796 | 2026-09-14 | 2026-09-15 |  |  | Released
21 | 5086+13 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 39" | 24 x 36 | 4865 | WO17802 | 2026-08-25 | 2026-08-27 |  |  | Released
21 | 5086+13 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17801 | 2026-09-12 | 2026-09-14 |  |  | Released
22 | 5088+48 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 29" | 24 x 36 | 4100 | WO17806 | 2026-08-25 | 2026-08-27 |  |  | Released
22 | 5088+48 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17805 | 2026-09-11 | 2026-09-14 |  |  | Released
23 | 5081+13 LT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 51" | 36 x 48 | 7327 | WO17787 | 2026-08-25 | 2026-08-28 |  |  | Released
23 | 5081+13 LT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17939 | 2026-08-28 | 2026-09-01 |  |  | Released
23 | 5081+13 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17786 | 2026-09-15 | 2026-09-16 |  |  | Released
23 | 5090+98 LT CBBI-MOD B1 | Base | 48" x 48" - BOX RISER 8inW- Variable Ht - 18" | 48 x 48 | 2707 | WO17810 | 2026-08-26 | 2026-08-28 |  |  | Released
23 | 5090+98 LT CBBI-MOD B1 | Base | 48" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 46" | 48 x 48 | 7512 | WO17811 | 2026-08-25 | 2026-08-29 |  |  | Released
23 | 5090+98 LT CBBI-MOD B1 | Base | 48" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 48 x 48 | 2170 | WO17940 | 2026-08-25 | 2026-08-27 |  |  | Released
23 | 5090+98 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 48 x 48 | 4000 | WO17809 | 2026-08-24 | 2026-08-25 |  |  | Released
24 | 5078+83 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 50" | 24 x 36 | 5976 | WO17785 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Built
24 | 5078+83 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17784 | 2026-09-16 | 2026-09-17 |  |  | Released
24 | 5092+83 LT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF - 54" | 36 x 48 | 7797 | WO17815 | 2026-08-25 | 2026-08-26 |  |  | Released
24 | 5092+83 LT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17941 | 2026-08-25 | 2026-08-27 |  |  | Released
24 | 5092+83 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17814 | 2026-08-25 | 2026-08-26 |  |  | Released
25 | 5077+33 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 35" | 24 x 36 | 4445 | WO17783 | 2026-08-22 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Built
25 | 5077+33 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17782 | 2026-09-17 | 2026-09-18 |  |  | Released
25 | 5094+66 LT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 45" | 36 x 48 | 6589 | WO17817 | 2026-08-27 | 2026-08-31 |  |  | Released
25 | 5094+66 LT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17942 | 2026-08-27 | 2026-08-28 |  |  | Released
25 | 5094+66 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17816 | 2026-08-26 | 2026-08-27 |  |  | Released
26 | 5095+00 LT JB-A | Base | 36" x 48" - CB FLAT TOP 8"W SOLID - 8" | 36 x 48 | 2234 | WO17818 | 2026-08-26 | 2026-08-27 |  |  | Released
26 | 5095+00 LT JB-A | Base | 36" x 48" - BOX BASE 8inW- 8inF - 42" | 36 x 48 | 5931 | WO17819 | 2026-08-25 | 2026-08-27 |  |  | Released
27 | 5096+43 LT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 41" | 36 x 48 | 6090 | WO17825 | 2026-08-28 | 2026-08-31 |  |  | Released
27 | 5096+43 LT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17943 | 2026-08-27 | 2026-08-31 |  |  | Released
27 | 5096+43 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17824 | 2026-08-27 | 2026-08-28 |  |  | Released
28 | 5097+50 LT CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 41" | 36 x 48 | 6265 | WO17827 | 2026-08-26 | 2026-08-28 |  |  | Released
28 | 5097+50 LT CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17944 | 2026-08-27 | 2026-08-28 |  |  | Released
28 | 5097+50 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17826 | 2026-08-28 | 2026-08-31 |  |  | Released
29 | 5098+23 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF - 42" | 24 x 36 | 5171 | WO17829 | 2026-08-26 | 2026-08-29 |  |  | Released
29 | 5098+23 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17828 | 2026-08-29 | 2026-08-31 |  |  | Released
30 | 5100+05 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 24 x 36 | 4763 | WO17836 | 2026-08-26 | 2026-08-28 |  |  | Released
30 | 5100+05 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17835 | 2026-08-31 | 2026-09-01 |  |  | Released
31 | 5101+20 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF - 30" | 24 x 36 | 4287 | WO17838 | 2026-08-27 | 2026-09-01 |  |  | Released
31 | 5101+20 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17837 | 2026-09-01 | 2026-09-02 |  |  | Released
32 | 4016+80 LT CBBI-MOD A1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17840 | 2026-08-27 | 2026-09-01 |  |  | Released
32 | 4016+80 LT CBBI-MOD A1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9A1 SAG - 17" | 24 x 36 | 4000 | WO17839 | 2026-08-20 | 2026-08-24 | 2026-08-21 | 2026-08-21 | Built
33 | 4016+28 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17842 | 2026-08-27 | 2026-09-01 |  |  | Released
33 | 4016+28 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17841 | 2026-09-02 | 2026-09-03 |  |  | Released
34 | 5102+27 LT DBI-10 MOD | Base | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 35" | 24 x 30 | 4354 | WO17834 | 2026-09-14 | 2026-09-16 |  |  | Released
34 | 5102+27 LT DBI-10 MOD | Base | 24" x 30" - BX FLAT LID 8inW w/16"x28" HOLE - 8" | 24 x 30 | 934 | WO17978 | 2026-09-08 | 2026-09-10 |  |  | Released
35 | 5102+98 LT DBI-10 MOD | Base | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 37" | 24 x 30 | 4371 | WO17833 | 2026-09-08 | 2026-09-10 |  |  | Released
35 | 5102+98 LT DBI-10 MOD | Base | 24" x 30" - BX FLAT LID 8inW w/16"x28" HOLE - 8" | 24 x 30 | 934 | WO17976 | 2026-09-08 | 2026-09-10 |  |  | Released
36 | 5074+83 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 33" | 24 x 36 | 4241 | WO17779 | 2026-08-26 | 2026-08-28 |  |  | Released
36 | 5074+83 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17778 | 2026-08-14 | 2026-08-17 | 2026-08-15 | 2026-08-15 | Built
36 | 5103+84 LT DBI-10 MOD | Base | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 37" | 24 x 30 | 4371 | WO17832 | 2026-09-11 | 2026-09-14 |  |  | Released
36 | 5103+84 LT DBI-10 MOD | Base | 24" x 30" - BX FLAT LID 8inW w/16"x28" HOLE - 8" | 24 x 30 | 934 | WO17977 | 2026-08-31 | 2026-09-02 |  |  | Released
37 | 4014+56 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 25" | 24 x 36 | 3776 | WO17846 | 2026-09-02 | 2026-09-04 |  |  | Released
37 | 4014+56 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17845 | 2026-09-03 | 2026-09-04 |  |  | Released
37 | 5074+83 RT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF - 30" | 24 x 36 | 4287 | WO17781 | 2026-08-17 | 2026-08-20 | 2026-08-18 | 2026-08-18 | Built
37 | 5074+83 RT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17780 | 2026-08-17 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Built
38 | 11+79 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 24 x 36 | 4955 | WO17777 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
38 | 11+79 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17776 | 2026-09-26 | 2026-09-28 |  |  | Released
38 | 14+27 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 42" | 24 x 36 | 5427 | WO17775 | 2026-08-24 | 2026-08-26 |  |  | Released
38 | 14+27 CBBI-MOD B1 | Base | 24" x 36" - BOX RISER 8inW- Variable Ht - 21" | 24 x 36 | 2143 | WO17882 | 2026-08-24 | 2026-08-26 |  |  | Released
38 | 14+27 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17881 | 2026-09-28 | 2026-09-29 |  |  | Released
38 | 4013+85 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3368 | WO17844 | 2026-09-04 | 2026-09-08 |  |  | Released
38 | 4013+85 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17843 | 2026-09-04 | 2026-09-08 |  |  | Released
39 | 15+26 CBBI-MOD B1 | Base | 24" x 36" - BOX RISER 8inW- Variable Ht - 54" | 24 x 36 | 5510 | WO17879 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
39 | 15+26 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 60" | 24 x 36 | 7263 | WO17880 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Built
39 | 15+26 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17878 | 2026-09-30 | 2026-10-01 |  |  | Released
39 | 5014+69 LT DBI-10 MOD | Base | 24" x 30" - BOX BASE 8inW- 8inF- Variable Ht - 35" | 24 x 30 | 4099 | WO17831 | 2026-09-10 | 2026-09-14 |  |  | Released
39 | 5014+69 LT DBI-10 MOD | Base | 24" x 30" - BX FLAT LID 8inW w/16"x28" HOLE - 8" | 24 x 30 | 934 | WO17945 | 2026-09-10 | 2026-09-14 |  |  | Released
40 | 15+26 DBI 2-MOD | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 46" | 36 x 48 | 7522 | WO17876 | 2026-08-17 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
40 | 4012+55 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 26" | 24 x 36 | 3878 | WO17848 | 2026-09-04 | 2026-09-08 |  |  | Released
40 | 4012+55 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17847 | 2026-09-08 | 2026-09-09 |  |  | Released
41 | 16+47 DBI 2-MOD | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 46" | 36 x 48 | 6934 | WO17877 | 2026-08-14 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
41 | 4010+98 LT CBBI-MOD B1 | Base | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 36 x 36 | 5381 | WO17857 | 2026-09-03 | 2026-09-08 |  |  | Released
41 | 4010+98 LT CBBI-MOD B1 | Base | 36" x 36" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 36 | 1235 | WO18135 | 2026-09-03 | 2026-09-08 |  |  | Released
41 | 4010+98 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 36 x 36 | 4000 | WO17856 | 2026-09-09 | 2026-09-10 |  |  | Released
42 | 5107+56 DBI TYPE 1-NA | Base | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 60" | 36 x 36 | 8077 | WO17863 | 2026-09-08 | 2026-09-11 |  |  | Released
43 | 4010+54 LT CBBI-MOD A1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 29" | 24 x 36 | 3845 | WO17853 | 2026-09-09 | 2026-09-11 |  |  | Released
43 | 4010+54 LT CBBI-MOD A1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9A1 SAG - 17" | 24 x 36 | 4000 | WO17852 | 2026-09-15 | 2026-09-18 |  |  | Released
44 | 17+62 CBBI-MOD B1 | Base | 36" x 48" - BOX BASE 8inW- 8inF- Variable Ht - 45" | 36 x 48 | 6922 | WO17875 | 2026-08-17 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
44 | 17+62 CBBI-MOD B1 | Base | 36" x 48" - CB FT REDUCER 24"X36" HOLE-FT - 8" | 36 x 48 | 1654 | WO17928 | 2026-08-15 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
44 | 17+62 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 36 x 48 | 4000 | WO17874 | 2026-10-01 | 2026-10-02 | 2026-08-25 | 2026-08-25 | Built
44 | 4010+04 LT CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 27" | 24 x 36 | 3896 | WO17855 | 2026-09-09 | 2026-09-12 |  |  | Released
44 | 4010+04 LT CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17854 | 2026-09-10 | 2026-09-11 |  |  | Released
45 | 18+23 CBBI-MOD A1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 40" | 24 x 36 | 4967 | WO17873 | 2026-08-17 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Built
45 | 18+23 CBBI-MOD A1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9A1 SAG - 17" | 24 x 36 | 4000 | WO17872 | 2026-08-18 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Built
45 | 4006+00 MH-A | Base | 48" - MH BASE - 30" | 48 | 3097 | WO17830 | 2026-08-31 | 2026-09-04 |  |  | Released
46 | 18+72 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 24 x 36 | 4763 | WO17871 | 2026-08-18 | 2026-08-20 | 2026-08-19 | 2026-08-19 | Built
46 | 18+72 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17870 | 2026-10-02 | 2026-10-03 |  |  | Released
47 | 19+71 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 35" | 24 x 36 | 4712 | WO17869 | 2026-08-17 | 2026-08-20 | 2026-08-18 | 2026-08-18 | Built
47 | 19+71 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 RH - 17" | 24 x 36 | 4000 | WO17868 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | Built
48 | 22+18 CBBI-MOD B1 | Base | 24" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 29" | 24 x 36 | 4100 | WO17867 | 2026-08-19 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Built
48 | 22+18 CBBI-MOD B1 | Top Phase | 24" x 120" - CB MED BAR BOX INLET 9B1 LH - 17" | 24 x 36 | 4000 | WO17866 | 2026-08-15 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Built
55 | 5116+07 RT DBI TYPE 1-MOD | Base | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 38" | 36 x 36 | 6050 | WO17864 | 2026-09-09 | 2026-09-11 |  |  | Released
56 | 5116+07 LT DBI TYPE 1-MOD | Base | 36" x 36" - BOX BASE 8inW- 8inF- Variable Ht - 28" | 36 x 36 | 4580 | WO17865 | 2026-09-09 | 2026-09-11 |  |  | Released
NO WORK ORDER ON THIS SALES ORDER - production dates not available in NetSuite for these lines:
| HWSF15 |  | 15in Sloped & Flared Headwall
| HWPC36 |  | 36in Pipe Culvert Headwall